## 00_Architecture
Research Workspace — Principal Architecture
Canonical architecture decisions and boundaries. This workbook is intended to be implemented directly and decomposed later into your own subphases.
Topic | Architecture Decision | Class | Status
Goal | One implementable research workspace combining a NotebookLM-style grounded mode and an autonomous deep-research mode over a shared memory + state fabric. | Decision | Locked
Core UX concept | Mode toggle: GROUND for source-grounded research and RESEARCH for autonomous multi-step investigation. Both operate on the same workspace. | Decision | Locked
Knowledge graphs | Two graphs only: Internal KG is exhaustive and operational; Research Output KG is a curated, user-visible semantic projection. | Decision | Locked
Citation graph | Removed as an independent graph. Citation/provenance are fields and relations on evidence/claims, not a separate graph. | Decision | Locked
Memory model | 6 logical memory systems; they are behaviors/ownership boundaries, not necessarily six databases. | Decision | Locked
State model | 8 state systems; state is mutable workflow/control information, not another copy of the knowledge base. | Decision | Locked
Schema philosophy | Typed core + extensible metadata. Mandatory fields are only those required for identity, ownership, provenance, lifecycle, or graph integrity. | Decision | Locked
Versioning | Git-like commits, branches, diffs and rollback at workspace/research state level, without literally storing every database row in Git. | Decision | Locked
Scratchpad | First-class working-memory surface; items can be promoted to research memory or graph knowledge after validation. | Decision | Locked
Free-tier strategy | Keep the logical architecture provider-agnostic and deploy a small physical stack first; scale individual stores independently. | Decision | Locked
UI scope | UI is intentionally outside this engineering inventory except for integration contracts and user-visible graph/state outputs. | Scope | Locked

## 01_Master_Architecture
Master Architecture & Implementation Inventory
Single source of implementation planning. One row = one component/contract boundary. The component can later be decomposed into your own subphases.
Layer | Domain | Component | Subcomponent | Purpose | Scope | Required Fields / Attributes | Optional Fields / Attributes | Source of Truth | Lifecycle | Build Strategy | Open-Source Reference | Initial / Free-Tier Tech | Scale / Future Tech | Migration Strategy | Dependencies | Key Failure Modes | Observability | Security / Governance | User Visible | Implementation Phase | Priority | Engineering Notes | Reference URL
Platform | Workspace | Workspace Service | Workspace lifecycle | Create, clone, archive and restore research workspaces | Workspace | workspace_id; owner_id; name; created_at; status | description; domain; default_mode; retention_policy | PostgreSQL | Long-lived | Build | PostgreSQL/Supabase | PostgreSQL via Supabase | Managed PostgreSQL / dedicated cluster | Keep repository interface stable; migrate DB provider without changing domain model | Auth; Versioning; Object Store | Orphaned data; accidental deletion | OpenTelemetry spans; audit events | Tenant isolation; row-level authorization; deletion policy | Yes | Phase 1 | P0 | Root aggregate for almost every resource | https://supabase.com/
Platform | Workspace | Project/Research Space | Workspace configuration | Store project-wide settings and conventions | Workspace | workspace_id; config_version; created_at | research_domain; terminology; citation_style; agent_defaults; retrieval_policy | PostgreSQL | Long-lived | Build | Pydantic; PostgreSQL | PostgreSQL | Managed PostgreSQL / config service | Version config objects; migrate by schema version | Workspace Service; User Memory | Config drift | Config change audit | RBAC; secrets excluded | Yes | Phase 1 | P0 | Keep configuration declarative | https://docs.pydantic.dev/
Platform | Identity | Authentication | User authentication | Authenticate users and establish tenant identity | Platform | user_id; provider; identity_ref; created_at | profile; auth_metadata | Auth provider | Long-lived | Reuse/Adapt | Supabase Auth | Supabase Auth free tier | Dedicated IdP / enterprise SSO | Wrap behind AuthProvider interface | Workspace; Authorization | Account takeover; stale sessions | Auth logs; failed-login metrics | MFA; token rotation | No | Phase 1 | P0 | Do not couple domain objects to auth provider | https://supabase.com/docs/guides/auth
Platform | Identity | Authorization | RBAC / workspace policy | Enforce user/workspace/resource permissions | Platform | principal_id; resource_id; action; decision | role; policy_source; reason | PostgreSQL policy layer | Per request | Build | Supabase RLS patterns | Postgres RLS | Dedicated policy engine if needed | Centralize authorization interface; policy data portable | Auth; Workspace | Over-permission; privilege escalation | Denied-action metrics; audit log | Least privilege; tenant isolation | No | Phase 1 | P0 | Separate authN from authZ | https://www.postgresql.org/docs/current/ddl-rowsecurity.html
Data | Object | Object Store | Source files | Immutable storage for PDFs, DOCX, images, audio and datasets | Workspace | object_id; workspace_id; object_uri; media_type; size_bytes; checksum; created_at | filename; tags; encryption_key_ref; retention_class | S3-compatible object storage | Long-lived | Reuse | S3 protocol | Supabase Storage / S3-compatible | AWS S3 / Cloudflare R2 / GCS | ObjectStore interface; checksum-stable keys; copy-on-migrate | Source Memory; Parsing | Corruption; missing object; duplicate uploads | Checksum metrics; object access logs | Encryption; signed URLs; malware scanning | Indirectly | Phase 1 | P0 | Object bytes must never be authoritative in graph DB | https://docs.aws.amazon.com/AmazonS3/latest/userguide/Welcome.html
Data | Ingestion | Source Registry | Source identity/versioning | Track logical source and immutable snapshots | Source | source_id; workspace_id; source_type; canonical_ref; created_at | title; author; publication_date; publisher; locale; tags | PostgreSQL | Long-lived | Build | Pydantic/Postgres | Postgres | Dedicated catalog if scale requires | Stable source IDs; snapshots additive, never overwritten | Object Store; Parsing | Duplicate source identity; stale metadata | Ingestion metrics; source freshness | Tenant scoping; provenance | Yes | Phase 1 | P0 | Source is logical identity; object is byte storage
Data | Ingestion | Snapshot Service | Immutable source snapshot | Preserve exact content used in a research run | Source | snapshot_id; source_id; object_id; checksum; captured_at | etag; headers; retrieval_method; content_hash | PostgreSQL + Object Store | Immutable | Build | S3 + Postgres | S3 + Postgres | Versioned object catalog | Content-addressed storage makes migration safe | Object Store; Source Registry | Snapshot mismatch; silent replacement | Checksum and freshness checks | Retention controls | Indirectly | Phase 1 | P0 | Critical for reproducible research
Data | Ingestion | Parser | Document extraction | Convert heterogeneous inputs to structured content | Source | source_id; parser_version; status; extracted_at | page_count; parser_warnings; language | Ingestion metadata in PostgreSQL | Per ingestion | Reuse/Adapt | Docling | Docling | Specialized parsers / managed OCR | Persist parser version + raw source so reprocessing is repeatable | Object Store; Queue | OCR/layout errors; unsupported formats | Parse success/error rate; latency | Sandbox untrusted files | No | Phase 1 | P0 | Docling is preferred broad document baseline | https://github.com/docling-project/docling
Data | Ingestion | Content Model | Document blocks | Normalize paragraphs, tables, images, equations and page locations | Source | block_id; source_id; block_type; sequence; text_or_ref | page_number; bounding_box; table_schema; formula_latex; confidence | PostgreSQL | Long-lived | Build/Adapt | Docling output + Pydantic | Postgres JSONB | Columnar/search-optimized store if needed | Canonical normalized block schema independent of parser | Parser; Chunking | Layout loss; malformed tables | Block validation; parser coverage | Sanitize embedded content | Indirectly | Phase 1 | P0 | This is the basis of source-grounded citations | https://github.com/docling-project/docling
Data | Ingestion | Chunker | Retrieval chunks | Produce bounded retrieval units while retaining source coordinates | Source | chunk_id; source_id; content; sequence; provenance_ref | token_count; heading_path; overlap; semantic_section | PostgreSQL | Long-lived | Build | Pydantic; tokenizer | Postgres + pgvector | Dedicated vector DB + search engine | Version chunker config; recompute embeddings/chunks without changing source IDs | Content Model; Embedding Service | Bad boundaries; citation drift | Retrieval quality; chunk size stats | No sensitive content in logs | Indirectly | Phase 1 | P0 | Chunk IDs should remain stable for identical content/config | https://github.com/pgvector/pgvector
Data | Ingestion | Metadata Enrichment | Source metadata extraction | Extract title/author/date/entities/topics | Source | source_id; schema_version; extraction_status | title; authors; dates; entities; topics; DOI; URL | PostgreSQL | Re-runnable | Reuse/Adapt | LLM structured extraction + Pydantic | Postgres | Batch enrichment pipeline | Store model/version and extraction run IDs | Parser; LLM Gateway | Hallucinated metadata | Extraction confidence; human corrections | Prompt/version audit | Indirectly | Phase 1 | P1 | Metadata is auxiliary, never source truth
Retrieval | Index | Vector Index | Chunk embeddings | Semantic retrieval over source chunks and knowledge objects | Workspace | index_id; object_id; vector; embedding_model; dimension | namespace; metadata_filter; created_at | Vector store derived from PostgreSQL objects | Rebuildable | Reuse/Adapt | pgvector | Postgres + pgvector | Qdrant / dedicated vector platform | EmbeddingProvider interface; backfill asynchronously; dual-write before cutover | Chunking; LLM Gateway | Model drift; stale embeddings | Recall@k; latency; index freshness | Tenant filters; no cross-tenant vectors | No | Phase 1 | P0 | Treat embeddings as derived cache, never canonical data | https://github.com/pgvector/pgvector
Retrieval | Index | Keyword Index | Lexical retrieval | Exact terminology, names, equations and identifiers | Workspace | document_id; field; term; position | language; boost | Search index | Rebuildable | Reuse/Adapt | PostgreSQL FTS | Postgres FTS | OpenSearch / Elasticsearch | SearchProvider abstraction; reindex from canonical DB | Source Registry; Chunking | Poor linguistic normalization | Search recall; query latency | Tenant scoped indexes | No | Phase 1 | P1 | Hybrid retrieval is preferable for research | https://www.postgresql.org/docs/current/textsearch.html
Retrieval | Pipeline | Hybrid Retrieval | Merge semantic + lexical retrieval | Improve retrieval robustness across technical and natural language queries | Workspace | query_id; candidate_ids; ranking_strategy | weights; rerank_model; filters | Retrieval event log | Per query | Build/Adapt | LangChain retrievers / custom ranker | Postgres + pgvector + FTS | Qdrant/OpenSearch + reranker | Preserve RetrievalService interface; A/B test implementations | Vector Index; Keyword Index; Reranker | Ranking instability; overfitting | Recall@k; MRR/NDCG; latency | Query filters; redaction | No | Phase 1 | P0 | This should remain independent from agent prompts | https://python.langchain.com/
Retrieval | Pipeline | Reranker | Second-stage ranking | Improve top-k evidence quality | Workspace | model_id; query_id; candidate_id; score | features; cutoff | Derived retrieval result | Per query | Reuse/Adapt | Cross-encoder or provider reranker | Small local/free model where feasible | Hosted reranker / larger cross-encoder | Config-driven provider; allow disable on cost constraints | Hybrid Retrieval | Latency; poor domain fit | nDCG; latency; cost | No raw query leakage | No | Phase 2 | P1 | Use after baseline retrieval is measured
Retrieval | Policy | Context Builder | Build grounded prompt context | Select evidence and package provenance-aware context | Run | run_id; selected_evidence_ids; token_budget | ordering; diversity_strategy; truncation_policy | Run State | Per run | Build | LangChain/LangGraph adapters | Python + Pydantic | Dedicated context optimization service | Keep context object serialized/versioned so behavior is reproducible | Retrieval; Evidence State; LLM Gateway | Context overflow; duplicate evidence | Context token count; evidence coverage | Prompt injection isolation | No | Phase 1 | P0 | Key bridge between RAG and agent | https://langchain-ai.github.io/langgraph/
Knowledge | Memory | Knowledge Memory | Canonical knowledge objects | Persistent semantic knowledge used across modes | Workspace | knowledge_id; knowledge_type; content; status; provenance; created_at | confidence; tags; entities; domain; version | PostgreSQL | Long-lived | Build | Pydantic/Postgres | Postgres | Dedicated knowledge service | Canonical KnowledgeStore interface; schema migrations additive | Source Memory; Research Memory; Graph projection | Duplicate or conflicting knowledge | Knowledge object counts; conflict rate | Provenance required for derived/extracted facts | Indirectly | Phase 1 | P0 | Core shared memory substrate
Knowledge | Memory | Source Memory | Source content references | Persistent access to source snapshots and source-derived units | Workspace | source_id; snapshot_id; object_ref | chunk_refs; parser_version; source_metadata | Source Registry/Object Store | Long-lived | Build/Adapt | Open Notebook ingestion concepts | Postgres + Object Store | Dedicated document service | Never rekey canonical source IDs during storage migration | Object Store; Parsing | Stale source pointer | Source freshness; integrity checks | Signed access | Indirectly | Phase 1 | P0 | One of six memory systems
Knowledge | Memory | Research Memory | Persistent research findings | Remember findings, hypotheses, conclusions and unresolved questions | Workspace | research_object_id; type; content; provenance; status; created_at | confidence; rationale; tags; linked_tasks | PostgreSQL + Research Output KG projection | Long-lived | Build | Pydantic/Postgres | Postgres + Neo4j | Knowledge service + graph store | Keep research IDs stable; graph is projection | Research State; Output KG | Stale conclusion; duplicate finding | Open/active finding counts; provenance coverage | Human approval states | Yes | Phase 1 | P0 | One of six memory systems
Knowledge | Memory | Episodic Memory | Important past research events | Recall meaningful actions, discoveries, failures and decisions without replaying all logs | Workspace | episode_id; event_type; summary; importance; created_at | run_id; task_id; outcome; entities; embedding_ref | Event log + summarized episodes | Long-lived | Build | Postgres + event schema | Postgres | Event store / stream platform | Summarize event history; retain raw events separately | Event Log; Run State | Memory bloat; noisy retrieval | Episode retrieval hit rate; compression ratio | Sensitive run data access control | No | Phase 2 | P1 | Do not stuff full event history into prompts
Knowledge | Memory | Working Memory | Current reasoning context | Hold temporary evidence, active hypotheses, tool results and intermediate context | Run | run_id; state_version; active_items; token_budget | scratch_items; pinned_items; expiry_at | Run State store | Ephemeral | Build | LangGraph state model | Postgres/Redis hybrid | Redis / workflow engine | Serialize state snapshots; TTL noncritical buffers | Run State; Context Builder | Context drift; runaway state | State size; checkpoint latency | Per-run isolation | No | Phase 1 | P0 | Should be summarized aggressively before model call | https://langchain-ai.github.io/langgraph/
Knowledge | Memory | User/Workspace Memory | Persistent human context | Store user notes, terminology, instructions and project conventions | Workspace/User | memory_id; owner_scope; content; status; created_at | tags; importance; visibility; expires_at | PostgreSQL | Long-lived | Build | Pydantic/Postgres | Postgres | Dedicated profile/memory service | Keep scope model explicit; no provider coupling | Workspace; Authorization | Stale preference; accidental leakage | Memory retrieval hit rate; age | User controls; deletion/export | Yes | Phase 1 | P1 | Sixth memory system; user-owned
Knowledge | Memory | Retrieval Representation | Derived memory index | Store summaries/embeddings/index references used to retrieve canonical memory | Workspace | representation_id; target_id; representation_type; version | embedding; summary; model_id; dimensions | Derived from canonical memory | Rebuildable | Build | pgvector/FTS | Postgres + pgvector | Qdrant/OpenSearch | Rebuild from canonical memory; no direct edits | Knowledge Memory; Retrieval | Stale indexes | Index freshness; rebuild status | No user-visible raw internals | No | Phase 1 | P1 | Counts as retrieval infrastructure, not another memory category
Orchestration | State | Workspace State | Active workspace state | Current active mode, selected sources, branches and workspace lifecycle | Workspace | workspace_id; active_branch; active_mode; state_version | selected_source_ids; UI-independent context refs | PostgreSQL | Long-lived | Build | Pydantic/Postgres | Postgres | State service | Version state; append-only event history | Workspace Service; Version State | Race conditions; lost updates | Optimistic lock conflicts | Tenant isolation | Indirectly | Phase 1 | P0 | One of eight state systems
Orchestration | State | Research State | Research objective/progress state | Track current objective, overall progress, findings and unresolved questions | Research | research_id; objective; status; state_version | milestones; open_questions; completion_reason | PostgreSQL | Long-lived | Build | Pydantic/Postgres | Postgres | Dedicated workflow state store | State machine with explicit transitions | Research Memory; Plan State | Invalid transition; stale progress | Transition errors; stale-state count | State transition authorization | Yes | Phase 1 | P0 | One state per research investigation
Orchestration | State | Plan State | Research plan | Represent current strategy, branches and planned subwork | Research Run | plan_id; version; steps; status; created_at | branch_id; rationale; estimated_cost | PostgreSQL/Run checkpoints | Versioned | Adapt/Build | LangGraph plan patterns | Postgres + LangGraph | Durable workflow engine | Plan version increments on mutation | Research State; Task State | Plan thrashing; orphan tasks | Plan revision count; branch count | Agent policy bounds | Yes | Phase 1 | P0 | Plan must be inspectable by user | https://langchain-ai.github.io/langgraph/
Orchestration | State | Task State | Individual research task lifecycle | Track subtasks, dependencies, retries and outcomes | Research | task_id; research_id; objective; status; parent_task_id | assigned_agent; priority; attempts; result_refs; blocked_reason | PostgreSQL | Long-lived | Build | Pydantic/Postgres | Postgres | Workflow engine task store | Stable task IDs; explicit transitions | Plan State; Run State | Deadlocks; duplicate execution | Task latency; retries; failure rate | Least privilege per task | Indirectly | Phase 1 | P0 | Supports parallel research
Orchestration | State | Run State | Current agent execution | Checkpoint an agent run for resume/replay/debugging | Run | run_id; task_id; step; status; state_version; started_at | checkpoint_ref; token_usage; model_id; stop_reason | Checkpoint store | Per run + retained history | Reuse/Adapt | LangGraph | LangGraph + Postgres/Redis | Durable workflow platform | Keep serialized checkpoint contract stable | Task State; Working Memory; Tool State | Lost checkpoint; non-determinism | Run duration; checkpoint frequency; resume success | Prompt/tool provenance; secret redaction | No | Phase 1 | P0 | Central execution state | https://langchain-ai.github.io/langgraph/
Orchestration | State | Tool State | Tool call lifecycle | Track search/browser/calculator/code tool calls and outcomes | Run | tool_call_id; run_id; tool_name; status; started_at | arguments_hash; result_ref; retry_count; latency; error_type | Event Log | Per run | Build/Adapt | OpenTelemetry + LangGraph events | Postgres/Redis | Event stream + tracing backend | Keep tool contract independent from provider | Run State; Event Log | Tool timeout; invalid arguments; injection | Latency; error rate; retries | Argument redaction; allowlist | No | Phase 1 | P0 | Do not store raw secrets
Orchestration | State | Evidence State | Evidence verification state | Track evidence validity, conflict, sufficiency and grounding status | Research | evidence_id; status; source_refs; state_version | confidence; reviewer; conflict_group; verification_notes | PostgreSQL + Internal KG | Long-lived | Build | Pydantic/Postgres | Postgres + Neo4j | Evidence service | Stable evidence IDs; explicit status transitions | Knowledge Memory; Retrieval; Output KG | Unsupported claim; conflicting sources | Evidence coverage; unresolved evidence count | Source provenance; reviewer controls | Yes | Phase 1 | P0 | Essential for trustworthy output
Orchestration | State | Graph State | Graph mutations | Track changes to Internal KG and Research Output KG | Workspace | graph_id; version; change_set_id; status | changed_node_ids; changed_edge_ids; projection_reason | Neo4j + Commit metadata | Versioned | Build/Adapt | Neo4j | Neo4j cluster / graph service | GraphStore abstraction; dual-write migration | Knowledge Memory; Version State | Partial graph update; projection drift | Graph mutation latency; orphan refs | Tenant graph isolation | Yes | Phase 1 | P1 | Output KG should be a curated projection | https://neo4j.com/
Orchestration | State | Version State | Git-like versions | Create commits, branches, diffs and rollback points | Workspace | commit_id; parent_commit_id; created_at; actor; message | branch; snapshot_ref; change_summary; merge_parent | PostgreSQL + Object Store | Long-lived | Build | Git concepts + Postgres | Postgres + Object Store | Dedicated version service / event store | Content-addressed snapshots; immutable commits | Graph State; Workspace State; Artifact State | Merge conflict; invalid parent | Commit rate; diff size; rollback success | Immutable audit trail; actor provenance | Yes | Phase 1 | P0 | Do not literally store full DB copy per commit | https://git-scm.com/docs
Knowledge Graph | Graph | Internal KG | Canonical operational graph | Machine-oriented graph containing detailed knowledge, provenance and execution relationships | Workspace | graph_id; node_id; node_type; edge_id; relation; source_ref; target_ref; created_at | confidence; temporal_validity; run_id; task_id; version; metadata | Neo4j | Long-lived | Build/Adapt | Neo4j; Graphiti patterns | Neo4j | Managed/dedicated graph cluster | GraphStore interface; batch export/import; preserve IDs | Knowledge Memory; Event Log; Evidence | Graph inconsistency; explosion in low-value edges | Node/edge counts; query latency; integrity scans | Tenant isolation; provenance access | No/diagnostic | Phase 2 | P0 | Internal graph may be detailed and ugly | https://neo4j.com/
Knowledge Graph | Graph | Internal KG | Core node taxonomy | Nodes for sources, claims, entities, findings, tasks, artifacts and events | Workspace | node_id; node_type; canonical_ref | label; summary; confidence; status; timestamps | Canonical object store | Long-lived | Build | Pydantic + Neo4j | Neo4j | Graph service | Projection from canonical objects | Knowledge Memory; State | Duplicate nodes; semantic drift | Node uniqueness checks | Access control by workspace | No | Phase 2 | P0 | Avoid creating nodes for transient noise unless useful
Knowledge Graph | Graph | Internal KG | Operational relation taxonomy | Detailed internal relationships including retrieval/provenance/version relations | Workspace | edge_id; source_id; target_id; relation_type | weight; confidence; created_at; run_id | Neo4j | Long-lived | Build | Neo4j | Neo4j | Graph query service | Version relation ontology | Run State; Version State | Relation explosion; ambiguous semantics | Edge counts by type; invalid-type checks | Provenance controls | No | Phase 2 | P1 | Use bounded relation vocabulary internally
Knowledge Graph | Graph | Research Output KG | Curated user-facing graph | Readable representation of meaningful research reasoning and outcomes | Workspace/Research | graph_id; projection_version; research_id | selected_node_types; layout_hint; display_filters | Projection derived from Internal KG | Versioned | Build | Neo4j + custom projection logic | Neo4j | Dedicated graph projection service | Output KG node IDs reference internal objects; regenerate projection safely | Internal KG; Research Memory; Evidence State | Too dense; stale projection | Projection coverage; user interaction telemetry | Expose only permitted data | Yes | Phase 2 | P0 | Small semantic relation vocabulary only
Knowledge Graph | Graph | Output KG | Visible relation vocabulary | Semantic edges that explain research without operational clutter | Research | relation_type; source_id; target_id | confidence; rationale; evidence_refs | Internal KG projected | Versioned | Build | Custom ontology | Neo4j | Graph ontology service | Keep vocabulary stable; additive evolution | Output KG | Too generic; visual clutter | Edge usefulness feedback | Provenance on every edge | Yes | Phase 2 | P0 | Recommended: supports, contradicts, derives_from, depends_on, explains, tests, relates_to, refines, extends, answers
Knowledge Graph | Graph | Output KG | Visual subsegments | Group graph into topic/finding/hypothesis/evidence clusters | Research | segment_id; research_id; title; node_refs | summary; confidence; segment_type | Research Output KG | Versioned | Build | Neo4j + graph layout logic | Neo4j | Graph analytics/visualization service | Segment IDs persist across projection versions when stable | Output KG; Research State | Too many segments; poor layout | Segment density; orphan segment count | User visibility policy | Yes | Phase 2 | P1 | This is important for usability
Knowledge Graph | Graph | Temporal Model | Validity/provenance time | Represent when information was true, discovered or superseded | Internal | valid_from; valid_to; observed_at; recorded_at | superseded_by; source_timestamp | Knowledge + event metadata | Long-lived | Build/Adapt | Neo4j temporal patterns / Graphiti concepts | Neo4j | Temporal graph platform | Keep temporal fields provider-neutral | Internal KG; Version State | Temporal ambiguity | Temporal query tests | Audit trail | No | Phase 2 | P1 | Do not conflate event time with record time | https://github.com/getzep/graphiti
Agent | Runtime | Agent Orchestrator | Research graph/workflow | Coordinate planning, retrieval, reasoning, tools, verification and synthesis | Run | run_id; workflow_id; input; status | max_iterations; budget; model_policy; stop_conditions | Run State | Per run | Reuse/Adapt | LangGraph; Open Deep Research patterns | LangGraph | Durable workflow engine / managed agent platform | Provider-independent node interfaces; persist checkpoints | Run State; Tool State; Memory | Loops; cost blowout; stalled graph | Run traces; token/cost metrics | Tool allowlists; sandboxing | No | Phase 1 | P0 | Core research agent should be adapted, not rewritten conceptually | https://langchain-ai.github.io/langgraph/
Agent | Runtime | Research Planner | Research decomposition | Convert user question into research plan and tasks | Run | objective; constraints; plan_id; steps | search_strategy; parallelism; budget | Plan State | Per run | Reuse/Adapt | Open Deep Research/STORM patterns | LangGraph + LLM | Model-based planner service | Plan schema stable; model swappable | Research State; Working Memory | Overplanning; missing subquestions | Plan quality evals; task coverage | Prompt injection isolation | No | Phase 1 | P0 | Planner should have explicit termination criteria | https://github.com/stanford-oval/storm
Agent | Research | Research Loop | Search-read-synthesize cycle | Iteratively gather and synthesize evidence until stop criteria | Run | run_id; iteration; objective; evidence_refs; status | max_iterations; query_set; saturation_score | Run State | Per run | Reuse/Adapt | GPT Researcher/STORM patterns | LangGraph + search tools | Distributed research worker fleet | Keep loop interface stable; externalize workers later | Planner; Retrieval; Web Tools | Research loops forever; shallow search | Coverage; novelty; saturation | Rate limiting; source policies | No | Phase 1 | P0 | Primary research behavior | https://github.com/assafelovic/gpt-researcher
Agent | Tools | Web Research | Search/open/browse | Gather current external evidence | Run | tool_call_id; query/url; result_ref; status | provider; citations; freshness; domain | Tool output objects | Ephemeral + retained evidence | Reuse/Adapt | Playwright + search APIs | Playwright + external search provider | Multiple search providers / browser fleet | ToolAdapter interface; provider failover | Tool State; Source Registry | Blocked pages; malicious pages; stale results | Success rate; latency; source freshness | Sandbox; URL allowlist; SSRF protection | Indirectly | Phase 1 | P0 | Browser and search are separate tools | https://playwright.dev/
Agent | Tools | Math Engine | Deterministic math | Solve symbolic/numeric tasks independently of LLM arithmetic | Run | expression/problem; result; method; status | assumptions; units; precision | Calculation artifact | Retained | Reuse | SymPy | SymPy/local Python | Sandboxed compute service | Keep calculation schema/provider-neutral | Tool State; Artifact Memory | Incorrect assumptions; timeouts | Correctness tests; execution time | Sandbox; resource limits | No | Phase 1 | P1 | LLM proposes; deterministic engine verifies | https://www.sympy.org/
Agent | Tools | Code/Compute Sandbox | Execute code for analysis | Run data analysis, charts and experiments safely | Run | execution_id; code_hash; environment_id; status | stdout_ref; stderr_ref; artifacts; package_manifest | Artifact/Object Store | Per run + retained artifact | Reuse/Adapt | Sandboxed Python/container runtimes | Container isolation | Dedicated sandbox service / Kubernetes jobs | Execution API independent of runtime provider | Tool State; Artifact Store | RCE; resource exhaustion | Execution failures; runtime | No network by default; syscall/resource limits | No | Phase 2 | P0 | Required for advanced research workloads
Agent | Verification | Evidence Verifier | Check claim-evidence alignment | Determine if generated statement is actually supported | Research/Run | claim_id; evidence_ids; verdict; score | rationale; model_id; verifier_version | Evidence State | Per claim + retained | Build/Adapt | LLM-as-judge + deterministic checks | Pydantic + evaluator models | Dedicated evaluation pipeline | Verifier interface; benchmark across model changes | Evidence State; Retrieval | False support; judge bias | Precision/recall on labeled support; drift | Do not expose hidden judge prompts | Indirectly | Phase 2 | P0 | Core trust mechanism
Agent | Verification | Contradiction Detector | Identify conflicting claims | Find incompatible claims across sources or within research | Research | claim_a; claim_b; verdict; evidence_refs | conflict_type; severity; rationale | Research Memory + Internal KG | Retained | Build/Adapt | Graph + LLM classifier | Neo4j + LLM | Specialized contradiction pipeline | Store contradiction objects; models replaceable | Claims; Evidence; Graph | False contradictions | Precision; reviewer agreement | Provenance | Yes | Phase 2 | P1 | Feeds Output KG as contradicts edges
Agent | Verification | Research Critic | Challenge plan/findings | Find gaps, unsupported assumptions and weak conclusions | Run/Research | target_id; critique; severity; status | suggested_action; rubric_id; model_id | Research Memory/Evidence State | Retained | Reuse/Adapt | LangChain eval patterns; custom critic | LangGraph + evaluator model | Evaluation service | Version rubrics and models | Research State; Evidence State | Critic hallucinations; endless critique | Critique usefulness; false-positive rate | Audit prompts/results | No | Phase 2 | P0 | Critic must feed actionable state mutations
Agent | Synthesis | Report Generator | Produce grounded/derived research output | Generate readable report with provenance-aware claims | Research | artifact_id; research_id; content; status | citation_style; section_outline; audience; format | Artifact Store + Research Memory | Versioned | Adapt | LLM structured generation; Open Notebook patterns | LLM gateway + templates | Dedicated report generation service | Keep artifact schema and section model stable | Evidence State; Output KG | Unsupported prose; citation mismatch | Claim coverage; citation coverage; factuality | Provenance; user approval | Yes | Phase 2 | P0 | Output should link back to KG nodes
Mode | Ground | Grounded Mode | Notebook/RAG engine | Answer strictly from workspace evidence with source provenance | Workspace/Run | mode; query; evidence_refs; answer; status | strictness; max_sources; response_style | Run State + Evidence State | Per turn | Reuse/Adapt | Open Notebook | Open Notebook + LangChain/LangGraph | Custom grounded answer service | Place behind Mode interface; do not fork core memory | Retrieval; Context Builder; Evidence | Hallucinated answers; citation drift | Groundedness evals; citation coverage | Source isolation; prompt injection | Yes | Phase 1 | P0 | Toggle changes execution policy, not workspace | https://github.com/lfnovo/open-notebook
Mode | Ground | Grounded Conversation | Contextual notebook chat | Multi-turn grounded conversation over selected sources | Session | session_id; messages; active_scope | pinned_sources; notes_ref | Conversation State + Source Memory | Session/retained | Reuse/Adapt | Open Notebook concepts | Postgres + LangGraph | Conversation service | Message schema portable; summarize history | Grounded Mode; User Memory | Context drift | Conversation retrieval quality | Tenant isolation | Yes | Phase 1 | P1 | Keep chat history separate from canonical knowledge | https://github.com/lfnovo/open-notebook
Platform | Mode Control | Mode Router | Ground/Research toggle | Route same workspace state into different execution policies | Workspace/Run | mode; workspace_id; run_id | reason; prior_mode; transition_event | Workspace State | Per interaction | Build | Custom router | FastAPI + LangGraph | Policy/orchestration service | Keep stable mode contract; add new modes later | Ground Mode; Research Mode; Shared State | State loss across toggle | Mode transition correctness | Authorization same across modes | Yes | Phase 1 | P0 | Toggle should not fork memory
Platform | Mode Control | Shared Context Contract | Common context between modes | Allow grounded and research modes to consume same canonical state | Run | workspace_id; selected_memory_refs; evidence_refs; graph_refs; state_version | mode-specific preferences | Shared Memory/State layer | Per run | Build | Pydantic | Postgres + Redis/LangGraph | Versioned context service | Contract tests across both modes | Memory; State; Graph | Context incompatibility | Contract tests; mismatch rate | No sensitive carryover across tenant scopes | No | Phase 1 | P0 | This is the architectural centerpiece | https://docs.pydantic.dev/
Infrastructure | Events | Event Log | Append-only domain events | Record state changes and significant actions | Workspace | event_id; event_type; aggregate_id; aggregate_type; occurred_at; actor | payload; causation_id; correlation_id; schema_version | PostgreSQL initially | Long-lived | Build | Event sourcing concepts | Postgres | Kafka/Redpanda/Pulsar at scale | Event envelope stable; stream to broker later | State; Versioning; Observability | Duplicate/out-of-order events | Lag; duplicate rate; schema failures | Immutable audit; redaction policy | No | Phase 1 | P0 | Do not event-source everything on day one
Infrastructure | Events | Commit Service | Git-like snapshot/commit creation | Persist coherent change sets across memory/graph/artifacts | Workspace | commit_id; parent_id; actor; timestamp; message; change_set | branch; tags; merge_parent; snapshot_ref | PostgreSQL + Object Store | Long-lived | Build | Git-inspired design | Postgres + S3 | Dedicated event/commit service | Immutable commit IDs; content-addressed changes | Event Log; Graph State; Artifact State | Partial commit; merge conflict | Commit validation; diff size | Immutable audit trail | Yes | Phase 1 | P0 | Research history should be reproducible | https://git-scm.com/
Artifacts | Artifact | Artifact Registry | Track generated outputs | Catalog reports, calculations, code, tables, datasets and exports | Workspace | artifact_id; workspace_id; artifact_type; uri; checksum; created_at; status | title; mime_type; size; version; provenance_refs | PostgreSQL + Object Store | Long-lived | Build | Pydantic + S3 | Postgres + object store | Artifact service / content-addressed store | Stable artifact IDs and checksums | Report Generator; Sandbox; Version State | Orphan artifacts; mismatch | Artifact integrity; creation latency | Signed URLs; malware scan | Yes | Phase 1 | P0 | Artifact is semantic object, not generic file
Artifacts | Artifact | Citation/Provenance Bundle | Bundle claim/source links for output | Provide explainability without separate citation KG | Artifact/Claim | claim_id; source_refs; locator; provenance_type | quote_ref; page; section; calculation_ref | Evidence State + Source Memory | Generated per output | Build | Custom schema | Postgres | Provenance service | Generate on output creation; regenerate from canonical evidence | Evidence State; Report Generator | Broken links; stale locators | Citation coverage; broken provenance rate | Source access policy | Yes | Phase 2 | P0 | This replaces need for a separate citation graph
Artifacts | Artifact | LaTeX/Paper Pipeline | Future scientific writing/compiler layer | Convert research state into publication-ready LaTeX artifacts | Research | artifact_id; document_class; source_refs; status | packages; bibliography_refs; build_logs | Artifact Store | Versioned | Build/Reuse | LaTeX toolchain later | Containerized LaTeX build | Prism-like hosted pipeline / sandbox | Artifact schema first; compiler implementation can change | Report Generator; Provenance | Compile failure; malicious source | Compile success; build time | Sandboxed compiler; no unrestricted shell | Yes | Phase 4 | P2 | Future scope; architecture should reserve artifact interfaces | https://www.latex-project.org/
Infrastructure | LLM | Model Gateway | Unified provider abstraction | Decouple product from any one model vendor | Run | provider; model; request_id; input; output; status | temperature; max_tokens; structured_schema; latency | Gateway request logs + artifacts | Per call + metrics | Reuse/Adapt | LiteLLM | LiteLLM | Provider router / model gateway | ProviderAdapter stable; record model/version | Agent; Ground Mode; Eval | Provider outage; model drift | Latency; cost; error rate; tokens | API key vault; no prompt secrets in logs | No | Phase 1 | P0 | Central cost/control point | https://github.com/BerriAI/litellm
Infrastructure | LLM | Structured Output | Schema-constrained generation | Produce typed claims/tasks/edges/state updates | Run | schema_name; schema_version; model_id; payload; validation_status | repair_attempts; raw_output_ref | Artifact/Event Log | Per call | Reuse/Adapt | Pydantic structured outputs | Pydantic + provider structured outputs | Schema registry/service | Version schemas; backward-compatible changes | LLM Gateway; State | Malformed JSON; schema drift | Validation failure rate | Prompt/output redaction | No | Phase 1 | P0 | Mandatory for reliable agent state mutation | https://docs.pydantic.dev/
Infrastructure | Caching | Response Cache | Cache deterministic/low-volatility calls | Reduce repeated retrieval/LLM/search cost | Platform | cache_key; value_ref; created_at; ttl | model_id; policy_version; tags | Redis | Ephemeral | Reuse | Redis | Redis free/self-hosted | Managed Redis / Redis Cloud | Cache interface + versioned keys; easy invalidation | LLM Gateway; Retrieval | Stale answer; cache poisoning | Hit rate; evictions; stale rate | Namespace/tenant keys | No | Phase 1 | P1 | Do not cache safety-sensitive user-specific responses blindly | https://redis.io/
Infrastructure | Async | Job Queue | Run long-running ingestion/research asynchronously | Decouple API latency from background workloads | Platform | job_id; type; payload_ref; status; created_at | attempts; priority; scheduled_at; worker_id | Postgres + Redis initially | Ephemeral + retained result | Reuse/Adapt | Celery/RQ/Redis | Redis + worker processes | Kafka + durable worker platform | Queue interface; idempotent jobs; later event broker | Ingestion; Agent; Artifact | Duplicate jobs; lost jobs | Queue depth; age; retry rate | Payloads by reference, not raw secrets | No | Phase 1 | P0 | Idempotency is mandatory | https://docs.celeryq.dev/
Quality | Evaluation | Offline Eval Suite | Measure retrieval, grounding and agent quality | Regression test system behavior | Platform/Research | eval_id; dataset_version; metric; expected; actual | task_type; model; prompt_version; notes | Git + dataset store | Versioned | Reuse/Adapt | LangChain/LangSmith evaluation ecosystem | Local eval harness + LangSmith optional | Dedicated eval platform | Dataset/version contracts; run same suite against new stack | Research; Retrieval; Agent | Metric gaming; benchmark drift | Pass rate; regressions; confidence intervals | Strip PII from datasets | No | Phase 2 | P0 | User said evals should be LangChain-based | https://docs.smith.langchain.com/
Quality | Evaluation | Online Eval | Production quality monitoring | Sample live traces for quality signals | Platform | trace_id; metric; evaluator_version; score; timestamp | sampling_rate; segment; feedback | Observability/Eval store | Retained | Reuse/Adapt | LangSmith + OpenTelemetry | LangSmith optional | Dedicated eval/observability platform | OpenTelemetry trace model; evaluator API independent | Tracing; Agent; Grounded Mode | Sampling bias; evaluator drift | Groundedness; citation coverage; failure rate | No raw sensitive prompts in external evals unless opted-in | No | Phase 2 | P1 | Separate operational observability from quality evaluation | https://docs.smith.langchain.com/
Quality | Evaluation | Human Review | User feedback/labeling | Collect corrections for claims, outputs and graph relationships | Research | review_id; target_id; reviewer; decision; created_at | rationale; corrected_value; labels | PostgreSQL | Long-lived | Build | Custom review schema | Postgres | Human labeling platform | Stable review schema | Research Memory; Evidence; Output KG | Reviewer bias; label inconsistency | Inter-rater agreement; correction rate | Reviewer permissions | Yes | Phase 2 | P1 | Feeds eval datasets and graph curation
Operations | Observability | Tracing | Distributed tracing of research runs | Track request→agent→tool→DB chain | Platform | trace_id; span_id; parent_id; timestamp | attributes; status; cost | OpenTelemetry collector/backend | Retained by policy | Reuse | OpenTelemetry | OpenTelemetry + local backend | Managed tracing platform | Provider-neutral instrumentation | Agent; API; DB; Queue | Missing spans; high cardinality | Trace completeness; latency | PII scrubbing | No | Phase 1 | P0 | Critical for debugging agents | https://opentelemetry.io/
Operations | Observability | Metrics | System and model metrics | Measure throughput, cost, quality and infrastructure health | Platform | metric_name; value; timestamp; dimensions | histogram; exemplar | Metrics backend | Retained | Reuse | OpenTelemetry metrics | OTel + Prometheus-compatible backend | Managed metrics platform | OpenTelemetry semantic conventions | All services | Cardinality explosion | SLOs; alerts | Avoid sensitive dimensions | No | Phase 1 | P1 | Measure cost per successful research output | https://opentelemetry.io/
Operations | Audit | Audit Log | Security and state audit trail | Record privileged actions and user-impacting mutations | Workspace | audit_id; actor; action; target; timestamp; outcome | ip_hash; reason; metadata | PostgreSQL append-only table | Long-lived | Build | Postgres | Postgres | Immutable audit platform | Append-only event envelope | Auth; Versioning; Admin | Tampering; missing events | Audit completeness; failed writes | Restricted access; retention | No | Phase 1 | P0 | Separate from verbose agent events
Security | Boundary | Prompt Injection Defense | Treat retrieved/web content as untrusted input | Prevent sources from controlling tools/system behavior | Run | source_id; trust_level; policy_version | matched_patterns; action | Security policy + run logs | Per run | Build/Adapt | OWASP patterns + custom | Application layer | Dedicated security gateway | Policy version in run record | Retrieval; Browser; Agent | Indirect injection; tool hijack | Blocked event counts; red-team evals | Isolation; allowlists | No | Phase 1 | P0 | Core research-agent security control | https://owasp.org/www-project-top-10-for-large-language-model-applications/
Security | Execution | Sandboxing | Restrict code/browser execution | Contain arbitrary or malicious content | Run | execution_id; policy_id; resource_limits | network_policy; filesystem_policy; timeout | Execution policy store | Per run | Reuse/Adapt | Container sandboxing | Docker isolation | Kubernetes sandbox/gVisor/Firecracker | Execution interface stable; stronger isolation later | Code Sandbox; Browser | RCE; data exfiltration | Security events; resource-limit violations | No host secrets; no unrestricted network | No | Phase 2 | P0 | Treat code and browser outputs as untrusted | https://docs.docker.com/engine/security/
Security | Data | Encryption/Secrets | Protect keys and sensitive data | Encrypt data at rest/in transit and isolate provider credentials | Platform | secret_ref; key_version; created_at | rotation_at; provider | Secret manager | Long-lived | Reuse | Cloud/Supabase secret mechanisms | Environment/managed secrets | Vault/KMS | Key versioning; envelope encryption | Auth; LLM Gateway; Object Store | Secret leak; expired key | Secret access metrics | KMS; rotation; least privilege | No | Phase 1 | P0 | Never put API keys in prompts/logs
Security | Data | Tenant Isolation | Prevent cross-workspace data leakage | Enforce workspace boundaries in DB/vector/graph/cache | Platform | workspace_id on tenant data | policy_version | DB RLS + application checks | Always | Build | Postgres RLS | Postgres RLS + application middleware | Dedicated multi-tenant isolation service | All stores require tenant context | Cross-tenant retrieval | Isolation tests; canary queries | RLS; scoped cache/index namespaces | No | Phase 1 | P0 | Mandatory for production readiness | https://www.postgresql.org/docs/current/ddl-rowsecurity.html
Architecture | Future-proofing | Provider Abstraction | Stable ports for external systems | Allow swapping LLM/search/vector/graph/object providers | Platform | provider_type; implementation; version | capabilities; config_ref | Configuration repository | Long-lived | Build | Ports/adapters architecture | Python interfaces + Pydantic | Service interfaces / platform contracts | Contract tests; dual-run implementations | All external dependencies | Tight coupling | Provider conformance tests | Secret isolation | No | Phase 1 | P0 | Every vendor dependency gets an adapter boundary
Architecture | Future-proofing | Schema Versioning | Evolve objects without breaking old runs | Version all event/object contracts | Platform | schema_name; schema_version; compatibility | migration_fn; deprecated_at | Git + migration registry | Long-lived | Build | Pydantic versioning patterns | Pydantic | Schema registry | Backward-compatible readers; explicit migrations | All domains | Breaking schema changes | Validation failures by version | Schema review | No | Phase 1 | P0 | Store schema version on persisted objects/events | https://docs.pydantic.dev/
Architecture | Future-proofing | Dual Write / Shadow Read | Migrate storage implementations safely | Run old/new backends in parallel and compare | Platform | migration_id; source_impl; target_impl; started_at; status | comparison_metrics; cutoff_at | Migration control DB | Temporary | Build | Custom | Application middleware | Migration orchestration service | Provider abstraction; evals | Divergent writes; hidden data loss | Comparison error rate; lag | No user-visible inconsistencies | No | Phase 3 | P0 | Primary path for pgvector→Qdrant or Postgres→distributed systems
Architecture | Future-proofing | Backfill Pipeline | Rebuild derived data after architecture changes | Recompute chunks, embeddings, summaries, graph projections | Platform | job_id; source_version; target_version; status | batch_size; checkpoint | Job Queue + source of truth | Temporary/re-runnable | Build | Celery/worker patterns | Redis workers | Distributed batch processing | Content-addressed inputs + checkpoints | Source Memory; Indexes; Graph | Incomplete backfill; duplicate outputs | Backfill progress; checksum mismatch | Write to new namespace first | No | Phase 3 | P0 | Critical for future model/index changes | https://docs.celeryq.dev/
Architecture | Future-proofing | Data Export | Portable workspace export | Avoid vendor lock-in and enable migration/backup | Workspace | workspace_id; export_version; manifest; checksum | compression; encryption; selected_scopes | Export manifest + Object Store | On demand | Build | JSON + Parquet + source files | ZIP/JSON/Parquet | Warehouse/object-storage export | Stable export schema | All domains | Missing dependencies in export | Export validation; restore tests | Encryption; signed exports | Yes | Phase 2 | P1 | Export should reconstruct logical workspace, not vendor DB internals
Technology | Runtime | Backend | API service | Primary product/backend service layer | Platform | service_name; version; health_status | build_sha; deployment_id | Git/CI metadata | Deployment | Reuse | FastAPI | FastAPI | Service mesh / managed compute | Container contract stable | Auth; Workspace; Agent | API overload | RPS; p95; errors | TLS; auth middleware | No | Phase 1 | P0 | Python keeps agent ecosystem close | https://fastapi.tiangolo.com/
Technology | Language | Backend | Python | Primary agent/data orchestration language | Platform | python_version | dependency_lock | Repo config | Deployment | Reuse | Python | Python 3.12-ish current supported version | Future supported version | Pin minor version; test upgrades | All Python services | Dependency incompatibility | Build/test metrics | Dependency scanning | No | Phase 1 | P0 | Keep core domain code framework-light | https://www.python.org/
Technology | Frontend | Web | Next.js/React/TypeScript | Application shell and research workspace UI | Platform | node_version; next_version | build_sha | Git | Deployment | Reuse | Next.js/React | Next.js/React | Edge/server runtime as needed | API contracts isolate frontend | API; Auth | Client state bugs | Web vitals; error rate | CSP; secure cookies | Yes | Phase 1 | P0 | UI excluded from requested design but stack belongs in system inventory | https://nextjs.org/
Technology | Database | Relational | PostgreSQL | Canonical transactional source of truth | Platform | db_version; migration_version | extensions | Database | Long-lived | Reuse | PostgreSQL | Supabase/Postgres free tier | Managed Postgres / Aurora etc. | SQL schema portable; migrations via Alembic/Flyway-style | All core data | Lock contention; storage growth | Connections; slow queries; bloat | RLS; encryption | No | Phase 1 | P0 | Preferred canonical store | https://www.postgresql.org/
Technology | Database | Vector | pgvector | Initial vector retrieval in Postgres | Platform | extension_version | index_type; dimension | Postgres | Derived/rebuildable | Reuse | pgvector | pgvector | Qdrant / vector service | VectorStore abstraction + reindex | Retrieval | Index growth; latency | Recall; p95; index size | Tenant filters | No | Phase 1 | P0 | Avoid separate vector DB until scale demands it | https://github.com/pgvector/pgvector
Technology | Database | Graph | Neo4j | Internal and Output KG storage | Workspace | neo4j_version; constraints | indexes; query_timeout | Graph store | Long-lived | Reuse | Neo4j | Neo4j AuraDB Free / local | Managed Neo4j cluster | GraphStore adapter; dump/export | Graph State; Knowledge | Graph hotspots; query cost | Query latency; node/edge count | Tenant partitioning / separate DBs | No | Phase 2 | P0 | Best fit for graph semantics | https://neo4j.com/
Technology | Cache | Redis | Cache/session/queue | Low-latency cache and background queue primitives | Platform | redis_version | modules | Redis (ephemeral) | Ephemeral | Reuse | Redis | Free/self-hosted / low-cost managed | Managed Redis cluster | CacheProvider + QueueProvider | Async; Cache | Eviction storms; persistence surprises | Hit rate; memory; queue depth | Namespacing; TLS | No | Phase 1 | P1 | Use as acceleration layer, never canonical truth | https://redis.io/
Technology | Storage | Object | S3-compatible | Binary source and artifact storage | Platform | bucket; object_key; checksum | storage_class | Object Store | Long-lived | Reuse | S3 API | Supabase Storage / R2 / S3 | AWS S3 / R2 / GCS | Portable URI scheme; export manifest | Sources; Artifacts | Orphan objects | Storage size; access rate | Encryption; signed URLs | No | Phase 1 | P0 | Use provider-neutral URIs | https://docs.aws.amazon.com/AmazonS3/latest/userguide/Welcome.html
Technology | Orchestration | Agent | LangGraph | Stateful agent graph/orchestration | Run | graph_id; state_schema; checkpoint | node_config; retry_policy | Run State | Per run + workflow definition | Reuse/Adapt | LangGraph | LangGraph | Managed agent/workflow platform or custom runtime | Persist checkpoint contract; isolate graph definitions | Agent; Run State | Infinite loops; checkpoint bloat | Node latency; retries; resumes | Tool policy; state redaction | No | Phase 1 | P0 | Core stateful orchestration technology | https://langchain-ai.github.io/langgraph/
Technology | Research | Notebook | Open Notebook | Baseline NotebookLM-like document/RAG subsystem | Workspace | repo_version; migration_version | custom_patches | Git fork/upstream merge | Long-lived | Reuse/Adapt | Open Notebook | Fork / upstream-compatible branch | Custom service boundaries + upstream merges as feasible | Keep custom memory/state APIs outside fork-specific internals | Ground Mode; Source Memory | Upstream divergence | Patch drift; integration tests | Review third-party changes | Yes | Phase 1 | P0 | Use as substrate, not as architectural authority | https://github.com/lfnovo/open-notebook
Technology | Research | Agent | STORM | Research planning/multi-perspective reference | Run | research_topic; outline; sources | perspectives; mind_map | Agent run outputs | Per run | Reuse/Adapt | Stanford STORM | Reference/selected modules | Custom planner/research orchestration | Extract concepts behind stable Agent interfaces | Research Planner; Output KG | Research loops; source quality | Research coverage; outline completeness | Source trust policy | No | Phase 1 | P1 | Use concepts; avoid coupling architecture to repo | https://github.com/stanford-oval/storm
Technology | Research | Agent | GPT Researcher | Autonomous research reference implementation | Run | task; sources; result | report_type; constraints | Agent outputs | Per run | Reuse/Adapt | GPT Researcher | Reference/selected components | Custom research workers | Tool/adaptor boundary | Research Loop; Web Research | Tool coupling; cost | Coverage; citation coverage | Browser sandbox | No | Phase 1 | P1 | Reference implementation, not core dependency | https://github.com/assafelovic/gpt-researcher
Technology | Documents | Parsing | Docling | Document parsing/layout/OCR baseline | Source | source_id; parser_version; status | options; warnings | Ingestion metadata | Per ingestion | Reuse/Adapt | Docling | Docling | Specialized parsing/OCR services | Parser adapter | Source Memory | Unsupported document edge cases | Parse success; table/formula extraction | Sandbox input files | No | Phase 1 | P0 | Strong base for PDFs and complex documents | https://github.com/docling-project/docling
Technology | Agent | Provider | LiteLLM | Unified LLM provider gateway | Platform | model; provider; request_id | fallbacks; routing_policy | Gateway config | Per call | Reuse | LiteLLM | LiteLLM | Dedicated model gateway | Provider-neutral request schema | LLM Gateway | Provider API changes | Error rate; cost | API key vault | No | Phase 1 | P0 | Avoid direct vendor coupling across codebase | https://github.com/BerriAI/litellm
Technology | Evaluation | Evals | LangSmith/LangChain evals | Evaluation traces and graders | Platform | eval_run_id; dataset; metric; score | feedback; rubric | Eval store | Per eval + retained | Reuse/Adapt | LangSmith | Local tests + optional LangSmith | Enterprise eval platform / self-hosted alternatives | Keep evaluator interfaces local-first | Evaluation | External eval latency/cost | Regression dashboard; score trends | Redact sensitive data | No | Phase 2 | P0 | Use LangChain ecosystem for evals as requested | https://docs.smith.langchain.com/
Technology | Observability | Telemetry | OpenTelemetry | Vendor-neutral traces, logs, metrics | Platform | trace_id; span_id; metric_name | attributes | Telemetry backend | Retained | Reuse | OpenTelemetry | OpenTelemetry + Prometheus-compatible backend | Managed observability | OTel instrumentation is portable | All services | High-cardinality telemetry | SLOs; trace coverage | PII filters | No | Phase 1 | P0 | Future-proof observability boundary | https://opentelemetry.io/
Technology | Execution | Browser | Playwright | Reliable web browser automation | Run | browser_session_id; url; action; status | browser_version; cookies_ref | Tool run artifacts | Per run | Reuse/Adapt | Playwright | Playwright | Browser fleet / managed browser service | BrowserTool interface | Web Research; Sandbox | Anti-bot blocks; browser compromise | Success rate; action latency | Isolated browser; no ambient credentials | No | Phase 1 | P0 | Browser should be treated as untrusted boundary | https://playwright.dev/
Data Contracts | Schema | Memory Envelope | Common memory record | Uniform envelope for all six memory classes | Workspace | memory_id; memory_type; scope_id; content_ref; provenance_ref; created_at | importance; status; expires_at; metadata | PostgreSQL | Long-lived or ephemeral by type | Build | Pydantic | Postgres | Schema registry | Memory systems; Versioning | Schema drift | Validation metrics | Tenant scope | No | Phase 1 | P0 | Memory type is semantic discriminator, not separate table necessarily | https://docs.pydantic.dev/
Data Contracts | Schema | Claim | Knowledge claim | Represent extracted/derived proposition with provenance | Workspace/Research | claim_id; text; claim_type; provenance_refs; status | confidence; subject_refs; predicate; object_refs; qualifiers | Knowledge Memory | Long-lived | Build | Pydantic/Postgres/Neo4j | Postgres + Neo4j | Knowledge service | Knowledge Memory; Evidence | Unsupported or duplicate claim | Claim validation; support ratio | Provenance mandatory | Yes | Phase 1 | P0 | Claim is semantic object; graph node is projection
Data Contracts | Schema | Evidence | Evidence reference | Represent source-backed support for a claim | Research | evidence_id; source_id; locator; content_ref; evidence_type; status | quote; page; timestamp; confidence; checksum | Source Memory + Evidence State | Long-lived | Build | Pydantic/Postgres | Postgres | Evidence service | Source Registry; State | Broken locator; stale snapshot | Evidence validity metrics | Source integrity | Yes | Phase 1 | P0 | Replaces separate citation graph
Data Contracts | Schema | Research Task | Unit of research work | Represent actionable subproblem | Research | task_id; objective; status; parent_task_id; created_at | priority; dependencies; assigned_to; budget; result_refs | Task State | Long-lived | Build | Pydantic/Postgres | Postgres | Workflow task store | Plan; Run | Deadlock; duplicate execution | Task transitions | Scoped tools | Indirectly | Phase 1 | P0 | Keep objective distinct from generated plan text
Data Contracts | Schema | Research Run | One agent execution | Immutable identity + mutable checkpoint state | Run | run_id; research_id; status; started_at; workflow_version | model_id; cost; stop_reason; parent_run_id | Run State + Event Log | Per run | Build | Pydantic/LangGraph | Postgres + LangGraph | Workflow engine | Run; Tool | Lost state; non-repeatability | Trace/run correlation | Secret redaction | No | Phase 1 | P0 | Research Run is execution envelope, not research itself
Data Contracts | Schema | Graph Node | Graph projection record | Map a domain object into graph representation | Graph | node_id; object_id; node_type; graph_id | label; summary; status; display_metadata | Canonical object + graph projection | Versioned | Build | Neo4j/Pydantic | Neo4j | Graph service | Knowledge; Output KG | Duplicate node | Uniqueness constraints | Access policy | No | Phase 2 | P0 | Do not duplicate semantic source of truth
Data Contracts | Schema | Graph Edge | Relationship record | Represent typed semantic/operational relationship | Graph | edge_id; graph_id; source_node_id; target_node_id; relation_type; created_at | confidence; provenance_refs; valid_from; valid_to; metadata | Neo4j projection | Versioned | Build | Neo4j/Pydantic | Neo4j | Graph service | Graph State | Relation ambiguity | Edge integrity checks | Tenant scope | No | Phase 2 | P0 | Output edge vocabulary smaller than internal vocabulary
Data Contracts | Schema | Event | State mutation/activity record | Represent atomic system event | Platform | event_id; type; aggregate_id; timestamp; actor; schema_version | payload; correlation_id; causation_id | Event Log | Append-only | Build | Pydantic/Postgres | Postgres | Event broker | All stateful services | Duplicate events | Event lag/duplicates | Immutable + redaction | No | Phase 1 | P0 | Do not store huge payloads inline; use refs
Data Contracts | Schema | Commit | Version checkpoint | Represent user/agent-visible research snapshot | Workspace | commit_id; parent_id; actor; created_at; message; change_set_ref | branch; merge_parent; tags; snapshot_ref | Version State | Immutable | Build | Postgres/Object Store | Postgres + S3 | Version service | Event Log; Graph State | Broken lineage | Commit integrity | Immutable audit | Yes | Phase 1 | P0 | Git-inspired semantics, not literal Git database
Data Contracts | Schema | Artifact | Generated research output | Represent report/code/calculation/table/etc. | Workspace | artifact_id; type; uri; checksum; status; created_at | title; mime_type; version; provenance_refs; build_ref | Artifact Registry/Object Store | Versioned | Build | Pydantic/S3 | Postgres + S3 | Artifact service | Agent; Sandbox | Orphan artifact | Checksum validation | Signed access | Yes | Phase 1 | P0 | Artifacts should be content-addressable when feasible
AI Context | Memory | Memory Router | Select memory by task and query intent | Retrieve only relevant memory classes to control prompt/token cost | Run | query; workspace_id; allowed_memory_types; token_budget | importance_threshold; recency_window; task_context | Run State | Per run | Build | Custom routing policy | Python + Redis/Postgres | Dedicated memory service | Policy version stored per run | All memory systems | Prompt bloat; irrelevant retrieval | Tokens per memory class; hit rate | No cross-scope retrieval | No | Phase 1 | P0 | Essential to prevent the six memories from polluting prompts
AI Context | Memory | Memory Compaction | Summarize/replace verbose working history | Compress working/episodic context while preserving important facts | Run/Workspace | input_refs; summary; kept_refs; policy_version | compression_ratio; discarded_refs | Canonical memories + summaries | Re-runnable | Build/Adapt | LLM summarization + deterministic retention | Python + LLM Gateway | Dedicated summarization worker | Never delete canonical source/claim objects automatically | Working; Episodic | Loss of crucial context | Retention tests; summary fidelity | Protected memory classes | No | Phase 2 | P0 | Prompt efficiency mechanism
AI Context | State | State Reducer | Compute next canonical state from events/results | Prevent agents from directly mutating arbitrary DB state | Run/Workspace | current_state; event; reducer_version; next_state | warnings; rejected_mutations | State Store | Per mutation | Build | Pure Python/Pydantic | Postgres | Event-sourced state engine | Reducers versioned and testable | Event Log; State systems | Invalid transition; race | Reducer test coverage; rejected mutations | Authorization before commit | No | Phase 1 | P0 | This is key to safe state evolution
Architecture | Decision | ADR | Open Notebook boundary | Define what is inherited vs replaced in Open Notebook | Platform | adr_id; decision; status; date | alternatives; consequences | Git | Long-lived | Build | ADR convention | Markdown in repo | Architecture decision system | Review on upstream updates | Open Notebook | Fork drift | ADR review cadence | Third-party license review | No | Phase 1 | P1 | Keep upstream-specific code behind adapters | https://github.com/lfnovo/open-notebook
Architecture | Decision | ADR | Graph ownership | Define canonical ownership of graph vs relational objects | Platform | adr_id; decision; status; date | alternatives; consequences | Git | Long-lived | Build | ADR convention | Markdown in repo | Architecture decision system | Review when graph model changes | Knowledge; Graph | Dual source of truth | Consistency tests | Access control | No | Phase 1 | P0 | Rule: Postgres/domain objects canonical; graph is projection
Architecture | Decision | ADR | Vector migration | Define trigger for pgvector→Qdrant | Platform | adr_id; migration_trigger; success_metrics | benchmark_window; rollback_plan | Git | Long-lived | Build | ADR convention | Markdown + metrics | Architecture decision system | Benchmark retrieval before migration | pgvector; Qdrant | Premature migration | Recall/latency/cost benchmark | Data migration policy | No | Phase 3 | P1 | Only migrate when scale/latency warrants it | https://qdrant.tech/
Governance | Provenance | Provenance Policy | Grounded vs derived labels | Explicitly distinguish source-backed, extracted, calculated and inferred information | Research | provenance_type; source_refs; derivation_refs; status | confidence; method; verifier | Knowledge/Evidence model | Long-lived | Build | Pydantic/Postgres | Postgres + Neo4j | Provenance service | Claim; Evidence; Output KG | Mislabeling derived data as source fact | Provenance completeness | Audit | Yes | Phase 1 | P0 | Core product trust model
Governance | Quality | Confidence Model | Store uncertainty without pretending it is truth | Attach confidence/status to claims and findings | Research | confidence_basis; score_or_class; version | calibration; evaluator; reviewer | Claim/Research Memory | Long-lived | Build | Custom schema | Postgres | Dedicated calibration service | Version confidence methodology | Evidence; Research State | False precision | Calibration error; score distribution | Explainability | Yes | Phase 2 | P1 | Use confidence classes where numeric score is unjustified
Governance | Quality | Human Approval | Promote findings to trusted output | Allow user to accept/reject/modify research findings | Research | review_id; target_id; decision; reviewer; created_at | reason; correction; prior_version | Postgres | Long-lived | Build | Custom review workflow | Postgres | Review service | Human review schema stable | Output KG; Version State | Accidental approval | Approval rate; reversion rate | Reviewer authorization | Yes | Phase 2 | P1 | Approval should create a commit/event
Core | Architecture | Domain Contracts | Typed core + extensible metadata | Define stable object envelopes with minimal mandatory fields and controlled extensibility. | All domains | id; type; workspace_id; created_at; updated_at; status; version; provenance_ref | metadata; domain_attributes; tags | PostgreSQL | Long-lived | Build | Pydantic | Pydantic + FastAPI | Versioned schemas + compatibility layer | Add schema_version and migration adapters; never couple API to physical DB shape | All domain services | Schema drift; breaking migrations | Schema validation errors; contract-test metrics | Explicit schema versions; backward compatibility | No | Phase 1 | P0 | Foundation for all memory/state/graph objects | https://docs.pydantic.dev/
Core | Memory | Shared Memory Fabric | Memory router | Select which of six memories to read/write for a task without injecting all memory into every prompt. | Memory layer | memory_type; scope; read_policy; write_policy | importance; freshness; confidence; token_budget; retrieval_filters | PostgreSQL + indexes | Long-lived + per-run | Build | LangGraph; Pydantic | PostgreSQL + pgvector | Dedicated memory service / tiered stores | Keep MemoryProvider interface stable; evolve routing policy independently | All memory stores; Retrieval | Prompt pollution; irrelevant retrieval; stale memory | Memory hit rate; relevance score; token budget usage | Tenant scoping; memory ACLs; audit writes | Partially | Phase 2 | P0 | Central abstraction to prevent prompt pollution
Core | State | State Engine | Reducers + transition validation | Maintain eight state domains with deterministic transitions and versioned checkpoints. | State layer | state_domain; entity_id; version; status; transition; updated_at | reason; actor; run_id; patch; checkpoint_ref | PostgreSQL | Mutable/versioned | Build | LangGraph state model | PostgreSQL + LangGraph checkpoints | Dedicated event/state service | Persist canonical state transitions behind StateStore interface | All agent workflows; Versioning | Race conditions; illegal transitions; lost updates | Transition failures; checkpoint latency; state divergence | Optimistic concurrency; audit trail | Partially | Phase 2 | P0 | State should be reducer-driven, not prompt-maintained
Core | Graph | Internal KG | Operational knowledge graph | Exhaustive machine-facing graph including evidence, provenance, extraction, intermediate and operational relations. | Graph layer | node_id; node_type; source_ref; workspace_id; created_at | confidence; timestamps; operational metadata | Neo4j / graph store | Long-lived | Build + Reuse | Neo4j | Neo4j Aura Free / graph abstraction | Managed Neo4j or compatible graph cluster | Use GraphStore interface; export/import graph snapshots | Knowledge Memory; Source Memory; Research Memory; State | Graph bloat; noisy relations; accidental exposure | Node/edge counts; traversal latency; orphan node rate | Workspace isolation; least-privilege credentials | No | Phase 3 | P0 | Do not expose raw Internal KG to end users | https://neo4j.com/
Core | Graph | Research Output KG | Curated research graph | User-visible semantic projection containing only useful research concepts and relations. | Research output | node_id; node_type; label; provenance_refs; status; version | confidence; summary; source_count; display_group; layout_hint | Projection from Internal KG + Research Memory | Versioned | Build | Neo4j + custom projection service | Neo4j + projection worker | Materialized views / dedicated graph service | Generate from projection rules; never make output graph the source of truth | Internal KG; Research Memory; Evidence State; Versioning | Overexposure; visual clutter; stale projection | Projection lag; user edits; broken provenance links | User-visible provenance; redact internal-only nodes | Yes | Phase 4 | P0 | Small semantic relation vocabulary; curated graph only | https://neo4j.com/
Core | Versioning | Research Version Control | Commit graph | Git-like commits, branches, diffs, merges and rollback for research workspaces. | Versioning | commit_id; workspace_id; parent_commit_id; created_at; actor; message | branch; change_set; tags; merge_parent_ids; snapshot_ref | PostgreSQL + object store | Long-lived | Build | Git concepts / JGit-inspired patterns | PostgreSQL + object storage | Dedicated version/event service | Stable commit/change-set model; archive snapshots to object store | State Engine; Graph State; Artifact State | Large diffs; merge conflicts; inconsistent snapshots | Commit duration; conflict rate; restore success | Immutable commit records; access-controlled branches | Yes | Phase 4 | P0 | Version logical state, not provider internals
Core | Execution | Research Orchestrator | Research graph runtime | Run multi-step planning, retrieval, browser/search, synthesis, validation and artifact generation workflows. | Agent runtime | run_id; research_id; objective; status; current_node; started_at | parent_run_id; model; trace_id; budget; checkpoint_ref | LangGraph checkpoints + PostgreSQL | Per-run + resumable | Adapt | LangGraph; STORM/GPT Researcher patterns | LangGraph + FastAPI | Distributed workers / queue-backed execution | Wrap orchestration behind domain workflow API | State Engine; Memory Fabric; Tools; Evals | Run hangs; retries amplify cost; state corruption | Trace spans; node latency; token/cost; retry count | Tool allowlists; budgets; sandboxing; secrets isolation | Partially | Phase 2 | P0 | Do not let model directly own persistent state | https://www.langchain.com/langgraph
Core | Notebook | Ground Mode | Source-grounded research mode | Retrieve source evidence, answer with exact provenance, preserve citations and avoid unsupported synthesis. | Ground mode | mode; query; source_scope; retrieval_policy | temperature; answer_length; citation_style | Grounding pipeline | Per interaction | Adapt | Open Notebook | Open Notebook + custom shared-state adapters | Dedicated RAG service if scale requires | Keep mode contract stable; replace internals incrementally | Source Memory; Knowledge Memory; Retrieval; Output KG | Hallucinated support; weak citations; stale index | Citation coverage; retrieval precision; groundedness eval | Strict source allowlist; source provenance required | Yes | Phase 4 | P0 | Prefer evidence-first prompt assembly | https://github.com/lfnovo/open-notebook
Core | Research | Research Mode | Autonomous research mode | Plan and execute multi-step research across internal and external sources, calculations and validation. | Research mode | mode; research_id; objective; source_policy | domain; budget; max_depth; search_scope | Research Orchestrator | Per run + persistent research memory | Adapt | STORM; GPT Researcher; Open Deep Research patterns | LangGraph + selected research components | Service-separated research workers | Abstract tools and planner interfaces | Research Orchestrator; Memory; Tools; Evals | Tool loops; weak source quality; context explosion | Research success; tool efficiency; evidence coverage | Tool policy; budgets; sandboxing; source trust policy | Yes | Phase 4 | P0 | Do not build autonomous research loop from zero | https://github.com/stanford-oval/storm
Core | Scratchpad | Research Scratchpad | Working notes | First-class temporary reasoning/work surface that can be promoted to durable research objects. | Working memory | scratchpad_id; workspace_id; content; created_at | type; links; promotion_target; author; run_id; tags | PostgreSQL | Ephemeral or promoted | Build | Custom | PostgreSQL | Document/knowledge service | Keep item IDs stable when promoting | Working Memory; Research Memory | Ephemeral notes lost; pollution of durable KG | Promotion count; stale item count | Workspace ACLs; user/system author attribution | Yes | Phase 2 | P1 | Scratchpad is not hidden chain-of-thought storage
Core | Evaluation | Evaluation Framework | Research/agent evals | Measure retrieval, groundedness, citation coverage, task completion, tool correctness, cost and graph quality. | Evaluation | eval_run_id; dataset_ref; metric; score; model; timestamp | slice; error_category; trace_ref; baseline; threshold | Evaluation store | Versioned | Reuse/Adapt | LangSmith / LangChain evals | LangSmith or local eval harness | Dedicated eval warehouse / CI eval service | Keep metric schemas provider-neutral; exporter adapters | Traces; Research Runs; Ground Mode; Research Mode | Goodharting; noisy labels; evaluation drift | Metric dashboards; regression gates | Evaluation data isolation; secrets redaction | No | Phase 5 | P1 | All production changes should have regression checks | https://www.langchain.com/langsmith/evaluation

## 02_Memory_6
Six Memory Systems
Logical memory behaviors, not six databases. Prompt assembly should retrieve a task-specific subset rather than load all memories.
Memory Type | Definition | What It Stores | Retrieval Behavior | Write Behavior | Retention | Canonical Source | Prompt Policy
Knowledge Memory | Durable semantic knowledge used across research. | Facts; concepts; entities; claims; relationships; validated findings. | Semantic + keyword + graph retrieval; task-filtered. | Validated promotion from source/research/working memory. | Long-lived | Postgres + Internal KG projection | Selective; retrieve only task-relevant objects; include provenance refs.
Source Memory | Immutable evidence substrate. | Files; webpage snapshots; document versions; pages; chunks; tables; images; source metadata. | Strict source retrieval; locator-aware. | Created by ingestion/reprocessing; immutable snapshots; supersession creates new version. | Long-lived | Object store + PostgreSQL | Grounded prompts retrieve exact source references and locators.
Research Memory | Persistent knowledge about investigations. | Research questions; findings; hypotheses; conclusions; unresolved questions; research summaries. | Research/task scoped + semantic. | Promote validated research outputs from runs and user edits. | Long-lived | PostgreSQL + Research Output KG projection | Retrieve current and historical research knowledge relevant to objective.
Episodic Memory | History of meaningful prior agent activity. | Prior runs; important actions; discoveries; failed approaches; decisions; notable tool outcomes. | Temporal + task similarity + recency. | Written from completed runs using summarization/promote rules; raw traces remain separate. | Long-lived with retention policy | PostgreSQL / trace index | Only important episodes; never dump entire history into prompts.
Working Memory | Temporary context for the current reasoning cycle. | Active evidence; current plan slice; hypotheses; scratchpad; tool results; unresolved subquestions. | Recency + task relevance; strict token budget. | Created/updated during a run; cleared or summarized on completion. | Ephemeral / checkpointed | LangGraph checkpoint + Redis where useful | Aggressive compression; explicit token budget; no silent persistent writes.
User / Workspace Memory | Human-controlled durable context. | Notes; project terminology; preferences; research conventions; custom instructions; curated facts. | Workspace scoped + explicit user retrieval. | User edits; agent suggestions require promotion/approval rules. | Long-lived | PostgreSQL | Use only when workspace/research context warrants it; never globalize tenant-specific data.

## 03_State_8
Eight State Systems
State is mutable control/workflow information. It must not become a second knowledge store.
State Type | Definition | Core Fields | Transitions | Retention | Canonical Store | Who Can Mutate
Workspace State | Current active research context. | workspace_id; active_branch; active_mode; state_version; status | created→active→archived | Long-lived | PostgreSQL | User + system
Research State | Overall investigation objective and progress. | research_id; objective; status; state_version; current_phase | planned→running→blocked→completed/abandoned | Long-lived | PostgreSQL | Agent through reducer + user
Plan State | Current research strategy and branch structure. | plan_id; version; steps; status; parent_plan_id | draft→active→revised→completed | Versioned | PostgreSQL / run checkpoints | Planner through reducer
Task State | Lifecycle and outputs of an individual research task. | task_id; research_id; objective; status; priority | queued→running→blocked→completed/failed/cancelled | Run lifetime + history | PostgreSQL | Orchestrator + reducer
Run State | Execution checkpoint for a specific agent run. | run_id; current_node; status; checkpoint_version; started_at | created→running→paused→completed/failed/cancelled | Run lifetime + checkpoint retention | LangGraph checkpoint + PostgreSQL | Orchestrator / reducer only
Evidence State | Reliability and validation state of evidence/claims. | evidence_id; validation_status; confidence; conflict_set_id | discovered→candidate→validated/contradicted/insufficient/superseded | Long-lived | PostgreSQL + graph projection | Validation services + controlled agent proposals
Graph State | Current and versioned graph projection state. | graph_id; graph_type; version; projection_version; status | building→projected→stale→reprojecting→current | Versioned | Graph store + PostgreSQL | Projection service; user edits through controlled mutations
Version State | Git-like commit, branch and snapshot state. | commit_id; branch; parent_commit_id; change_set_ref; author; message | created→committed→branched→merged/reverted | Long-lived immutable history | PostgreSQL + object snapshots | Only versioning service can create commits; users/agents request commits

## 04_Core_Contracts
Canonical Core Data Contracts
Mandatory fields are minimal and structural. Optional fields are controlled extensions. GraphNode/GraphEdge are projections, not canonical knowledge objects.
Object | Hard Required Fields | Optional / Extensible Fields | Owner | Design Rule
Workspace | workspace_id; owner_id; status; created_at; updated_at | name; description; domain; default_mode; retention_policy; settings_ref | Workspace service | Root tenant/project aggregate.
Source | source_id; workspace_id; source_type; canonical_uri_or_object_ref; version; created_at | title; author; publisher; language; published_at; checksum; access_policy; metadata | Source memory / ingestion | Immutable logical source; updates create versions.
SourceSnapshot | snapshot_id; source_id; content_ref; checksum; captured_at | raw_headers; crawl_metadata; parser_version; extraction_version | Object store + source service | Exact evidence snapshot used for reproducibility.
Chunk | chunk_id; source_snapshot_id; locator; content_ref; created_at | embedding_ref; token_count; section_path; page; table_ref; metadata | Source memory | Retrieval unit; must retain precise locator.
MemoryItem | memory_id; memory_type; scope_id; content_ref; provenance_ref; created_at | importance; status; expires_at; confidence; metadata | Memory fabric / relational store | Envelope for six memory systems; semantic payload varies by memory_type.
Claim | claim_id; workspace_id; text; claim_type; provenance_refs; status; created_at | confidence; subject; predicate; object; qualifiers; tags; contradiction_set | Knowledge memory | Never detach claim from provenance.
Evidence | evidence_id; source_id; locator; content_ref; evidence_type; status; created_at | quote; page; timestamp; confidence; checksum | Source memory / evidence state | Not a separate graph; evidence is an object with provenance.
Entity | entity_id; canonical_name; entity_type; workspace_id; created_at | aliases; description; external_ids; attributes | Knowledge memory / Internal KG | Deduplicated subject representation.
Finding | finding_id; research_id; statement; status; provenance_refs; created_at | confidence; impact; supporting_claims; contradicting_claims; notes | Research memory | Primary unit of research output.
Hypothesis | hypothesis_id; research_id; statement; status; created_at | support_refs; contradiction_refs; test_plan_ref; confidence; rationale | Research memory | Can evolve through version history.
Research | research_id; workspace_id; objective; status; created_at | domain; constraints; source_policy; budget; output_requirements | Research service | Top-level investigation aggregate.
ResearchTask | task_id; research_id; objective; status; created_at; updated_at | parent_task_id; assignee; priority; dependencies; result_refs; budget | Task state | Atomic/sub-atomic execution goal.
ResearchRun | run_id; research_id; objective; status; started_at; ended_at | parent_run_id; model; trace_id; token_budget; tool_budget; checkpoint_ref | Run state + traces | One orchestration execution.
ToolInvocation | tool_call_id; run_id; tool_name; status; requested_at; completed_at | arguments_ref; result_ref; retry_of; error_type; latency_ms | Run trace / event store | Operational trace; not user knowledge by default.
Calculation | calculation_id; research_id; expression_or_method; inputs_ref; result_ref; created_at | units; assumptions; engine; verification_status; precision | Research memory / artifact store | Deterministic computation should be reproducible.
Artifact | artifact_id; research_id; type; content_ref; status; version; created_at | title; mime_type; parent_artifact_id; checksum; approval_state | Artifact store | Reports, tables, code, figures, LaTeX sources, exports.
GraphNode | node_id; graph_id; object_type; object_ref; label | display_group; summary; confidence; layout_hint; metadata | Graph projection | Projection of canonical objects; not source of truth.
GraphEdge | edge_id; graph_id; source_node_id; target_node_id; relation; created_at | confidence; provenance_refs; valid_from; valid_to; display_weight | Graph projection | Relations are typed but deliberately small in Output KG.
Event | event_id; workspace_id; event_type; actor_id; occurred_at | entity_ref; payload_ref; trace_id | Event/audit store | Immutable operational record; not all events become memory.
Commit | commit_id; workspace_id; branch; parent_commit_id; author; message; created_at; change_set_ref | merge_parent_ids; tags; snapshot_refs; diff_stats | Versioning service | Immutable logical history.
ScratchpadItem | scratchpad_id; workspace_id; content; created_at; status | type; links; author; run_id; promotion_target; tags | Working memory / workspace | Not hidden chain-of-thought; user-visible notes and structured thinking artifacts.

## 05_Internal_KG
Internal Knowledge Graph — Canonical Machine Graph
This graph is intentionally comprehensive and operational. It is not the client-facing visualization. It stores relationships needed for provenance, investigation history, retrieval and reconstruction.
Node Type | Canonical Object | Purpose | Persisted | Notes
Source | Source / SourceSnapshot | Source of evidence; immutable origin. | Yes | Canonical object refs; not display-oriented.
Document | Source / Artifact | Logical document or imported file. | Yes | Can contain versions/snapshots.
Chunk | Source | Retrieval unit with exact locator. | Yes | High-volume; never expose directly unless useful.
Table | Source | Structured source table. | Yes | Supports row/cell locators.
Entity | Knowledge | Canonical entities. | Yes | Deduplicated.
Claim | Knowledge | Extracted or validated proposition. | Yes | Always provenance-aware.
Evidence | Knowledge/Source | Specific supporting fragment. | Yes | Can include quote/page/timestamp.
Research | Research | Investigation aggregate. | Yes | Links research state.
Task | Research | Research task/subtask. | Yes | Operational provenance.
Finding | Research | Validated research result. | Yes | Candidate for Output KG.
Hypothesis | Research | Testable/competing explanation. | Yes | Can branch and evolve.
Calculation | Research | Deterministic analysis artifact. | Yes | Inputs and method are explicit.
ToolInvocation | Execution | Operational tool action. | No | Internal-only debugging/provenance.
Run | Execution | Agent execution. | No | Internal operational trace.
Commit | Versioning | Version-control object. | No | Supports historical reconstruction.
Artifact | Research | Generated report/code/table/figure/etc. | Yes | Output candidate.

## 06_Internal_KG_Edges
Internal KG — Relationship Catalog
Internal relationship vocabulary may be richer than the visible Research Output KG. These relations exist for machine reasoning, provenance and reconstruction.
Source Type | Relation | Target Type | Meaning
SourceSnapshot | version_of | Source | Preserve exact source lineage.
Chunk | part_of | SourceSnapshot | Hierarchy.
Chunk | contains | Evidence | Evidence extraction.
Evidence | supports | Claim | Grounding relation.
Claim | about | Entity | Semantic subject.
Claim | contradicts | Claim | Conflict detection.
Research | has_task | Task | Investigation structure.
Task | produced | Finding | Task result.
Task | tested | Hypothesis | Explicit test relation.
Finding | derived_from | Claim | Research synthesis.
Finding | derived_from | Evidence | Evidence lineage.
Calculation | calculated_from | Evidence / Claim / Artifact | Reproducible analysis.
ResearchRun | executed | ResearchTask | Run provenance.
ToolInvocation | invoked_by | ResearchRun | Operational trace.
ToolInvocation | retry_of | ToolInvocation | Retry chain.
Commit | captures | State / Graph change set | Versioning.
Artifact | generated_from | ResearchRun / Finding / Calculation | Output provenance.
Artifact | supersedes | Artifact | Version lifecycle.
Hypothesis | refined_from | Hypothesis | Research evolution.
Task | blocked_by | Task / Evidence | Operational blockage.

## 07_Output_KG
Research Output KG — User Visible Semantic Graph
Curated projection of internal knowledge. Keep the relation vocabulary intentionally small so the graph remains intelligible.
Node Type | Examples | Purpose | Default Visibility | Useful Attributes
Source | Paper / Dataset / Web Source | Evidence origin visible to researcher. | Usually | summary; author; date; provenance
Entity | Person / Organization / Concept / Method | Semantic entity. | Usually | aliases; description
Claim | A sourced proposition. | Core knowledge node. | Always | claim_type; confidence; source_refs
Finding | Research conclusion synthesized from evidence. | Primary research-result node. | Always | confidence; methodology; supporting_refs
Hypothesis | Open/proposed explanation. | Optional | status; confidence; tests
Calculation | Derived quantitative result. | Optional | method; inputs; result; verification
Question | Open research question. | Optional | status; priority
Artifact | Report/table/figure/code/etc. | Optional | artifact_type; version

## 08_Output_KG_Edges
Research Output KG — Curated Relationship Vocabulary
Do not expose retries, branches, raw tool events, storage internals or raw chunk topology as first-class user graph edges. Operational history is surfaced through version/timeline views instead.
Relation | Typical Direction | Meaning
supports | Evidence/Claim → Claim/Finding | Indicates evidence supports a proposition.
contradicts | Claim/Finding ↔ Claim/Finding | Indicates explicit conflict.
derives_from | Finding/Calculation → Claim/Evidence | Shows derivation lineage.
depends_on | Finding/Calculation/Artifact → Claim/Finding/Calculation | Important dependency.
tests | Evidence/Experiment → Hypothesis | Shows that evidence/tests a hypothesis.
explains | Finding/Claim → Finding/Phenomenon | Connects explanation to target.
answers | Finding → Question | Question resolution.
refines | Finding/Claim → Claim/Finding | More precise version.
extends | Finding/Claim → Claim/Finding | Builds beyond existing result.
relates_to | Any semantic node ↔ Any semantic node | Weak/neutral relation.
associated_with | Entity/Claim/Finding ↔ Entity/Claim/Finding | Non-causal association when supported.

## 09_Shared_Memory_State
Shared Memory + State Interaction Model
This is the integration contract between Notebook/Ground mode and autonomous Research mode. It prevents both modes from maintaining disconnected contexts.
Trigger | Memory Read | State Change | Write Rule | Primary IDs | Engineering Rule
User asks question | Conversation + Workspace State | Create/continue Research State | No persistence of hidden reasoning | Question/Research IDs | Research request becomes explicit state.
GROUND mode query | Working Memory + Source Memory + Knowledge Memory | Run State + Evidence State | No graph mutation unless promotion occurs | Evidence refs | Strict source scope and citation requirements.
RESEARCH mode query | Research + Episodic + Working Memory | Plan + Task + Run State | Agent proposes mutations; reducers commit | Run/Task IDs | Multi-step investigation.
Agent finds evidence | Source Memory + Working Memory | Evidence State | Candidate evidence object | Evidence ID | Validation before durable promotion.
Agent creates finding | Working/Research Memory | Research State + Graph State | Promote only after provenance validation | Finding ID | Finding links to evidence/claims.
Scratchpad note | Working Memory + Workspace Memory | Workspace/Run State | User-controlled promotion | Scratchpad ID | Not automatically durable.
Run completes | Episodic Memory | Run State→completed; Version State commit | Summarized episode; raw trace retained separately | Commit ID | Only meaningful outcomes promoted.
Output graph refresh | Knowledge/Research Memory | Graph State projection | Generate curated graph | Projection version | Output KG is materialized view.
User edits conclusion | User/Workspace Memory + Research Memory | Research + Graph + Version State | Commit diff | Commit ID | Human correction has clear provenance.
Rollback | Version State | Workspace + Graph State | Restore snapshot/change set | Commit ID | Do not mutate historical commits.

## 10_Agent_Research
Agent + Research System Components
Reuse mature components for parsing, orchestration, research patterns, browser automation and evaluation. Build the product-specific memory, provenance, state and graph layers.
Component | Mode | Primary Responsibility | Build Strategy | Technology / Reference | Reads/Writes
Planner | Research mode | Plan objective into tasks; maintain branchable strategy. | Adapt | LangGraph + STORM-style decomposition | Plan State; Task State; Research Memory
Retriever | Both | Retrieve source/evidence/knowledge using hybrid signals. | Reuse/Adapt | Open Notebook retrieval + pgvector | Working Memory; Source Memory; Evidence State
Web/Search | Research | Search external sources and rank candidate evidence. | Reuse/Adapt | Search API(s) + provider adapters | Source Memory; Working Memory
Browser Executor | Research | Open, inspect and interact with web pages when search snippets are insufficient. | Reuse/Adapt | Playwright | Tool/Run State
Document Parser | Both | Convert documents into structured content, layout, tables, formulas and chunks. | Reuse/Adapt | Docling | Source Memory
Claim Extractor | Both | Extract atomic propositions from evidence. | Build | Pydantic + LLM structured output | Claim Memory; Evidence State
Evidence Validator | Both | Validate provenance, source alignment and conflicts. | Build | Rules + LLM judge + retrieval checks | Evidence State; Internal KG
Synthesis Agent | Both | Turn validated evidence into findings/answers while preserving provenance. | Adapt | LLM + LangGraph | Research Memory; Output KG
Math/Compute Worker | Research | Perform reproducible calculations, symbolic math and numeric checks. | Reuse/Adapt | SymPy + Python sandbox | Calculation; Artifact
Code/Analysis Worker | Research | Run controlled analysis over datasets or code. | Reuse/Adapt | Python sandbox / container | Artifact; Calculation
Citation/Provenance Layer | Both | Attach source refs and provenance metadata to claims; not a separate graph. | Build | Custom provenance service | Claim; Evidence; Output KG
Graph Projector | Both | Materialize Internal KG and curated Output KG from canonical objects. | Build | Neo4j + projection rules | Graph State
Memory Router | Both | Select relevant memory types and enforce token/relevance budgets. | Build | Custom + embeddings/rules | Working Memory
Reflection/Summarizer | Research | Compress completed runs into episodic/research memory. | Build | LangGraph + LLM | Episodic; Research Memory
Evaluation Harness | All | Evaluate retrieval, groundedness, agent task completion, citations, tools, cost. | Reuse/Adapt | LangSmith / LangChain evals | Eval store

## 11_Ground_RAG
GROUND / Notebook-RAG System
NotebookLM-like source-grounded functionality should be adapted from Open Notebook rather than reimplemented from zero.
Subsystem | Capability | Implementation Need | Strategy | Primary Technology
Ingestion | Files / URL / media ingestion | Register source, store immutable snapshot, extract structure. | Adapt | Open Notebook + Docling + object storage
Chunking | Structure-aware chunking | Create locator-aware retrieval units. | Adapt | Docling + custom chunk policy
Indexing | Keyword + vector indexing | Enable hybrid retrieval. | Adapt | Postgres FTS + pgvector initially
Ground Retrieval | Evidence retrieval | Retrieve source-grounded evidence for current question. | Adapt | Hybrid retrieval + graph filters
Context Builder | Prompt context assembly | Construct source-bounded context within token budget. | Build | Custom
Citation Binding | Claim-to-source linkage | Every grounded claim has provenance refs. | Build | Custom provenance contract
Grounded Answer | Answer synthesis | Produce concise evidence-grounded response. | Adapt | LLM + Open Notebook patterns
Notebook Artifacts | Summaries / study aids | Generate source-grounded artifacts. | Adapt | Open Notebook features
Source Refresh | Re-fetch / reprocess | Create new source snapshots without destroying history. | Build + Reuse | HTTP loaders / parser pipeline

## 12_Tech_Stack
Technology Stack + Future-Proofing
Free-tier-first physical stack with explicit abstraction boundaries. Replace infrastructure independently as scale requires.
Category | Initial Choice | Why Initial | Scale / Future | Migration Trigger | Abstraction Boundary
Frontend / API boundary | Next.js + React + TypeScript | Mature product surface | Managed deployment / edge as needed | Traffic/latency | HTTP API + schema contracts
Backend | FastAPI + Python | Agent + data ecosystem | Service decomposition or workers | Traffic / team growth | Domain service interfaces
Agent orchestration | LangGraph | Stateful graph execution | Distributed worker pool | Concurrent runs | Workflow interface
Notebook / RAG base | Open Notebook | Existing NotebookLM-like functionality | Fork/adapt or carve service boundaries | Product divergence | Adapter over shared contracts
Research methodology | STORM / GPT Researcher patterns | Research planning and evidence synthesis | Custom research workers | Research depth/cost | ResearchWorkflow interface
LLM gateway | LiteLLM or equivalent | Provider/model abstraction | Managed routing / gateway | Model fleet complexity | LLMProvider interface
Structured schemas | Pydantic | Typed core contracts | Versioned schema package | Schema evolution | OpenAPI / JSON Schema
Primary DB | PostgreSQL (Supabase initially) | Canonical source of truth; pgvector | Managed Postgres cluster | Storage/connections/throughput | Repository layer
Graph DB | Neo4j Aura Free initially | Native graph traversal | Managed/dedicated Neo4j | Graph size/query load | GraphStore interface
Vector search | pgvector initially | Avoid premature extra system | Qdrant / dedicated vector DB | Vector scale/latency | VectorStore interface
Cache | Redis | Caching, locks, short-lived state, queues | Redis cluster / managed Redis | Throughput + HA | Cache/Queue interface
Object storage | S3-compatible storage | Large immutable source/artifacts | Managed S3 / tiered object storage | Storage/egress | ObjectStore interface
Document parsing | Docling | PDF/document structure, tables, formulas | Managed workers / specialized parsers | Throughput | Parser interface
Browser automation | Playwright | Web navigation/extraction | Browser worker pool | Concurrent browsing | BrowserTool interface
Math | SymPy | Deterministic symbolic/numeric computation | Dedicated compute workers | CPU needs | Compute interface
Async jobs | Celery + Redis or equivalent | Long-running tasks | Dedicated queue/broker | Throughput/reliability | Job interface
Observability | OpenTelemetry | Tracing and metrics | Managed observability platform | Scale/cost | Telemetry API
Evals | LangSmith / LangChain evals | Agent/RAG evaluation and regressions | Dedicated evaluation pipeline | Dataset volume | Evaluation schema
Auth | Supabase Auth or equivalent | Fast initial identity/auth | Enterprise IdP | SSO/compliance | AuthProvider
Secrets | Managed secret env / vault | API keys and credentials | Vault / cloud secret manager | Compliance | SecretProvider
CI/CD | GitHub Actions | Automated tests/deploys | Enterprise CI/CD | Org needs | Pipeline interface
Deployment | Docker | Reproducibility | Kubernetes / managed containers | Scale and isolation | Container contract

## 13_Build_vs_Reuse
Build vs Reuse — What You Actually Need to Engineer
The principle is to reuse mature infrastructure/agent patterns and build the product-specific shared memory, state, provenance, graph projection and version-control layers.
Component | Capability | Decision | Custom Engineering | Boundary
Open Notebook | Notebook/RAG baseline | Adapt | Source ingestion, notebook semantics, source chat, provider wiring, UI/API integration | Shared source/memory/state contracts
LangGraph | Agent orchestration | Reuse + build workflows | Research graph nodes, reducers, checkpoint policy, tool routing | Workflow API
STORM | Research methodology | Reference/adapt | Multi-perspective research decomposition and knowledge curation | Research workflow interface
GPT Researcher | Research patterns | Reference/adapt | Parallel research patterns, source gathering, report synthesis | Research service API
Open Deep Research | Deep research reference | Reference only | Planner/tool/research state ideas; do not depend on archived repo | Research workflow contracts
Docling | Document parsing | Reuse | Parser adapters and chunk policy | Parser interface
Playwright | Browser | Reuse | Safe browser worker, extraction policy, auth/session handling | Browser tool interface
SymPy | Math | Reuse | Sandbox and deterministic result wrapper | Compute interface
Neo4j | Graph database | Reuse | Graph schema, indexes, projection queries | GraphStore interface
PostgreSQL/pgvector | Relational + vector | Reuse | Schema, repositories, hybrid retrieval | Repository/VectorStore interface
Redis | Cache/queue | Reuse | Cache keys, queue semantics, locks | Cache/Queue interface
LangSmith | Observability/evals | Reuse + integrate | Datasets, traces, evaluator definitions, regression gates | Evaluation adapter
Pydantic | Contracts | Reuse | Domain models, validation, JSON schema | Schema package
OpenTelemetry | Telemetry | Reuse | Spans/metrics/log correlation | Telemetry API
Supabase Auth | Identity | Reuse initially | OAuth, session handling, RLS where applicable | AuthProvider
Custom Memory Fabric | Shared memory | Build | 6 memory router, promotion policies, retrieval budgets | MemoryProvider
Custom State Engine | Shared state | Build | 8 state domains, reducers, transitions, checkpoint/replay | StateStore
Custom Provenance | Grounding + research provenance | Build | Claim/evidence lineage, source locators, audit | Provenance API
Custom Graph Projection | Output KG | Build | Internal→Output filtering, relation vocabulary, user visibility | Projection API
Custom Versioning | Git-like research history | Build | Commit/change-set/branch/merge/rollback semantics | VersionControl API
Custom Research Output UX contract | Graph/timeline integration | Build | Data/API only in this architecture inventory | Output API

## 14_6_Phase_Plan
Six-Phase Implementation Plan
Six macro phases only. You can divide each phase into your own subphases, sprints, milestones and tickets.
Phase | Name | Objective | Major Deliverables | Exit Criteria | Priority | Architecture Note
Phase 1 | Foundations + canonical data layer | Freeze domain model; workspace/auth; Postgres; object storage; Pydantic contracts; source ingest; schema versioning; repository interfaces; baseline observability; Docker/CI. | Workspace Service; Auth; Object Store; Source; SourceSnapshot; Chunk; Core schema package; Repository layer; OpenTelemetry bootstrap. | Architecture tests; migrations; source snapshot round-trip; contract tests; auth isolation; CI green. | P0 | No agent intelligence yet beyond basic parsing.
Phase 2 | Shared Memory + State + Orchestration | Implement six memory systems and eight states; Memory Router; State Engine; reducers; checkpoints; scratchpad; LangGraph orchestration; run/task lifecycle; event model. | Knowledge/Source/Research/Episodic/Working/User memory; Workspace/Research/Plan/Task/Run/Evidence/Graph/Version state. | State transition tests; replay test; checkpoint/resume; prompt token-budget tests; memory retrieval precision baseline. | P0 | This creates the common substrate both modes will share.
Phase 3 | Internal KG + Ground Mode | Build Internal KG, evidence/provenance, hybrid retrieval, document grounding, source-bound answers, claim extraction, evidence validation, internal graph synchronization. | Internal KG; Evidence; Claim; Entity; GraphStore; hybrid retrieval; provenance service; Ground Mode. | Citation/provenance tests; graph integrity; retrieval evals; groundedness baseline; source version reproducibility. | P0 | Output KG not yet exposed; keep graph comprehensive and internal.
Phase 4 | Research Mode + Output KG + Version Control | Integrate research planner, web/search/browser, math/code workers; research memory; findings/hypotheses; curated Output KG; Git-like commits/branches; timeline and graph projection APIs. | Research Mode; ResearchTask/Run; Calculation; Findings; Hypotheses; Output KG; projector; commits/diffs/rollback. | End-to-end research scenarios; failure/retry handling; graph projection correctness; restore from commit; budget enforcement. | P0 | Now the product's differentiated research workflow exists.
Phase 5 | Evaluation + Reliability + Scale Separation | Build LangSmith eval datasets; regression gates; quality metrics; cost/latency dashboards; security hardening; queue workers; cache; load tests; provider/model routing; migration adapters. | Evaluation harness; Redis; async jobs; observability; policy engine; migration abstractions. | Offline eval suite; canary runs; rate-limit tests; recovery drills; data isolation tests; cost budgets. | P1 | Do not scale physical infrastructure before metrics show where the bottleneck is.
Phase 6 | Production hardening + Migration readiness | Extract scalable services only where needed; dedicated vector store if required; managed graph/DB; object storage lifecycle; HA; disaster recovery; data export/import; tenant controls; plugin/provider adapters. | Service boundaries; dedicated Qdrant if justified; managed Redis; managed Neo4j/Postgres; backup/restore; export/import; enterprise auth. | SLOs; DR restore; upgrade rehearsal; backward compatibility; migration dry-runs; security review; incident runbooks. | P1 | Phase is for production durability, not adding random features.

## 15_Migration
Migration + Future-Proofing Strategy
Migration is designed as interface substitution, not a rewrite. Scale only the physical implementation whose metrics require it.
Current | Future Option | Why / Trigger | Stable Boundary | Migration Approach
Postgres via Supabase | Managed Postgres cluster | When storage/connections/throughput exceed free-tier operational needs. | Keep SQL domain model and Repository interfaces stable. | Add read replicas/connection pooling; later move provider using CDC/dump restore.
pgvector | Qdrant / dedicated vector service | When vector size/latency/filtered search outgrows Postgres. | VectorStore interface + stable embedding metadata. | Dual-write and shadow-read, compare results, cut over by workspace.
Neo4j Aura Free | Managed/dedicated Neo4j | Graph size, query concurrency, or HA requirements. | GraphStore interface; graph schema versioned. | Export/import snapshots; dual environment; validate counts/hashes.
Redis single instance/free tier | Managed Redis cluster | Throughput/HA or multi-worker locks/queues. | Cache/Queue interface. | Move keyspace/persistence policy; retain cache semantics.
Local/hosted object store | Managed S3 | Storage, lifecycle, bandwidth or compliance. | ObjectStore interface; content-addressed refs. | Replicate then flip object resolver.
Supabase Auth | Enterprise IdP | SSO/SCIM/compliance requirements. | AuthProvider interface; domain stores subject ID only. | Map external identity IDs; session cutover.
Single API service | Worker/service separation | Queue depth/latency and team ownership grow. | Domain service interfaces + event contracts. | Extract one bounded context at a time without changing API contract.
Single research model | Model router / multi-model | Cost, quality or specialization needs. | LLMProvider interface; model metadata in Run State. | A/B providers; preserve evaluation dataset and output contract.
Local eval runner | LangSmith / managed evals | Team size and eval volume increase. | Evaluation schema provider-neutral. | Export datasets and scores; compare metric semantics.
Direct graph queries in app code | Graph service/repository | Graph logic becomes complex or reused by multiple services. | GraphStore + query modules. | Move traversal rules behind repository/service boundary.

## 16_NFR_Evals
Non-Functional Requirements, Security & Evaluation
The architecture is research-grade only if correctness, provenance, reproducibility, isolation and run recovery are first-class.
Requirement | Target | Priority | Implementation / Test
Correctness | Grounded answer claims must point to valid evidence locators. | P0 | Claim/evidence provenance validator; regression dataset
Reproducibility | Research calculations and source snapshots must be replayable. | P0 | Snapshot checksums; deterministic compute wrappers; commit restore tests
Isolation | Workspace/tenant data must never cross retrieval boundaries. | P0 | workspace_id mandatory; policy filters; authorization tests
Prompt efficiency | Do not inject all memory/state into prompts. | P0 | Memory Router; relevance threshold; token budget; summarization
Resumability | Long research runs recover after process failure. | P0 | LangGraph checkpoints; idempotent tasks; retry policy
Auditability | Important changes must be attributable. | P0 | Event log; commit history; actor metadata
Graph integrity | No dangling canonical refs from graph nodes/edges. | P0 | Consistency jobs; referential validation
Output clarity | Research Output KG must remain small and semantically interpretable. | P1 | Projection rules; relation allowlist; node visibility policy
Security | API keys and tool credentials never enter prompts/state payloads. | P0 | SecretProvider; redaction; secret refs
Tool safety | Browser/code tools must be constrained. | P0 | Allowlist; sandbox; network restrictions; execution budget
Cost control | Every run has token/tool/time budgets. | P1 | Run State budgets; model router; usage events
Evaluation | Changes require regression evaluation. | P1 | LangSmith/local eval harness; CI thresholds

## 17_ReadMe
Implementation Guide / How to Navigate
This workbook intentionally keeps the architecture unified while preserving detailed contracts in separate sheets. Nothing here should be treated as a disconnected mini-project.
Topic | Guidance
How to use this workbook | Start with 00_Architecture, then 01_Master_Architecture. The remaining sheets are implementation contracts, not independent fragments.
What is canonical? | Core objects in 04_Core_Contracts are canonical. Graph nodes/edges are projections. Memory and state are logical domains with canonical stores.
What gets built? | 13_Build_vs_Reuse identifies the product-specific pieces: Memory Fabric, State Engine, provenance, graph projection and versioning.
How to phase work? | 14_6_Phase_Plan has exactly six macro phases. Split each into your own subphases without changing the architecture boundaries.
How to scale? | 12_Tech_Stack plus 15_Migration show when and how to replace free-tier components while keeping provider-neutral interfaces.
What not to build? | Do not build a new notebook UI/RAG platform, parser, browser automation engine, math engine, graph database or generic agent framework from scratch.
Important graph rule | Internal KG is comprehensive; Research Output KG is curated and user-visible. Citation/provenance is a data capability, not a third graph.
Important schema rule | Mandatory fields should be identity/ownership/lifecycle/provenance/graph integrity fields only. Optional metadata handles domain-specific variation.